## Gantt Chart
First Point of Contact / Website
| Conestoga Design Limited |  | Project Start: | 2020-02-13
| Team 2 |  | Today: | 2020-03-20
|  |  | Display Week: | 1 |  |  | 2020-02-10 | [6 empty] | 2020-02-17 | [6 empty] | 2020-02-24 | [6 empty] | 2020-03-02 | [6 empty] | 2020-03-09 | [6 empty] | 2020-03-16 | [6 empty] | 2020-03-23
 | time axis 2020-02-10 to 2020-03-29
| TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2020-02-10 to 2020-03-29
A. Project Management Plan
1 | Develop overall Project Management Plan | Devangi, Harjot | 100% | 2020-02-20 | 2020-02-20 | 1
1.1 | Prepare Project Planning Document | Devangi, Harjot | 100% | 2020-02-21 | 2020-02-21 | 1
B. Tools
2 | Develop RACL Version 1 Chart Spreadsheet | Devangi, Harjot | 100% | 2020-02-21 | 2020-02-21 | 1
2.1 | Develop RACL Version 1 Content | Devangi, Harjot | 100% | 2020-02-21 | 2020-02-21 | 1
3 | Develop Team Contract Content | Bhupinder | 100% | 2020-02-21 | 2020-02-22 | 2
3.1 | Prepare Team Contract Document | Bhupinder | 100% | 2020-02-21 | 2020-02-22
C. Project Management Documents
4 | Develop Project Scope Content | Suneel | 100% | 2020-02-21 | 2020-02-24 | 4
4.1 | Prepare Project Scope Document | Suneel | 100% | 2020-02-25 | 2020-02-25 | 1
| Element 1: Client Background | Harjot | 100% | 2020-02-25 | 2020-02-25 | 1
4.2 | CDL Background & History | Devangi | 100% | 2020-02-25 | 2020-02-25 | 1
4.3 | Stakeholder List and description | Bhupinder | 100% | 2020-02-25 | 2020-02-25 | 1
4.4 | Current CDL business challenges | Akshay | 100% | 2020-02-25 | 2020-02-25 | 1
4.5 | List of Brands Involved | Suneel | 100% | 2020-02-26 | 2020-02-26 | 1
| Element 2: Scope | Devangi | 100% | 2020-02-26 | 2020-02-29
| Element 3: Tools and Techniques | Devangi | 100% | 2020-02-28 | 2020-03-01
5 | Work breakdown structure | Suneel | 100% | 2020-02-23 | 2020-02-25
| Element 4: Considerations | Devangi, Harjot | 100% | 2020-03-04 | 2020-03-04
6 | Risk List | Devangi, Harjot | 100% | 2020-03-04 | 2020-03-04
6.1 | Style Guide for Application | Devangi, Harjot | 100% | 2020-03-04 | 2020-03-04
6.2 | Project Team Performance | Harjot | 100% | 2020-03-04 | 2020-03-04
6.3 | Assumptions | Devangi | 100% | 2020-03-04 | 2020-03-04
| Element 5: Report Components Content | Devangi | 100% | 2020-03-04 | 2020-03-04
7 | Cover Letter | Harjot | 100% | 2020-03-06 | 2020-03-06
7.1 | Cover Page | Suneel | 100% | 2020-03-06 | 2020-03-06
7.2 | Document History Chart | Suneel | 100% | 2020-03-06 | 2020-03-06
7.3 | TOC | Suneel | 100% | 2020-03-06 | 2020-03-06
7.4 | Document Formatting | Suneel | 100% | 2020-03-06 | 2020-03-06
| Element 6: Submission Quality | All Team members | 100% | 2020-03-06 | 2020-03-06
D. Submission Element
8 | History of CDL | Devangi | 100% | 2020-02-25 | 2020-02-25
8.1 | List and descriptions of actors/ stakeholders | Devangi | 100% | 2020-02-25 | 2020-02-25
8.2 | As-Is Principles of CDL | Devangi | 100% | 2020-02-25 | 2020-02-25
8.3 | Current business challenges of CDL | Harjot | 100% | 2020-02-25 | 2020-02-25
9 | Gifts, skills,attitudes of actors/stakeholders | Devangi, Bhupinder | 100% | 2020-02-26 | 2020-02-26
9.1 | Implementation strategy | Suneel | 100% | 2020-03-10 | 2020-03-15
9.2 | Agile methodology | All Team members | 100% | 2020-02-26 | 2020-02-26
9.3 | Develop Use Cases Contents | Devangi | 100% | 2020-03-10 | 2020-03-10
9.4 | Prepare Use Case diagram | Harjot | 100% | 2020-03-10 | 2020-03-13
9.5 | Cockburn template for each interaction | Devangi | 100% | 2020-03-17 | 2020-03-17
10 | Current website screens and its functional documentation | Akshay | 100% | 2020-03-17 | 2020-03-18
10.1 | Identified flaws or issues | Akshay | 100% | 2020-03-11 | 2020-03-11
10.2 | The known client requirements | Suneel | 100% | 2020-03-11 | 2020-03-11
10.3 | Build prototype and navigation | Harjot, Suneel | 100% | 2020-03-12 | 2020-03-12
10.4 | Prototype content | Devangi, Harjot | 100% | 2020-03-13 | 2020-03-13
10.5 | Annotating prototype | Akshay | 100% | 2020-03-14 | 2020-03-14
10.6 | Menumap creation | Akshay | 100% | 2020-03-15 | 2020-03-15
10.7 | Functional documentation | Bhupinder | 100% | 2020-03-18 | 2020-03-18
10.8 | Create pseudocode | Devangi, Bhupinder | 100% | 2020-03-18 | 2020-03-18
10.9 | Valiate and update changes in pseudocode | Devangi, Harjot | 100% | 2020-03-18 | 2020-03-18
11 | As-Is process flow | Bhupinder | 100% | 2020-03-18 | 2020-03-18
11.1 | To-be process flow | Harjot | 100% | 2020-03-19 | 2020-03-19
11.2 | Job descriptions of Website devlopers | Suneel | 100% | 2020-03-19 | 2020-03-19
11.3 | Project budget | Suneel | 100% | 2020-03-20 | 2020-03-20
11.4 | End users and customers- definition | Harjot, Suneel | 100% | 2020-03-20 | 2020-03-20
11.5 | Brief list of risks and benefits associated with the website creation | Devangi, Bhupinder | 100% | 2020-03-20 | 2020-03-20
11.6 | Metrics to determine website success or failure | Akshay | 100% | 2020-03-20 | 2020-03-20
| Risk analysis and Impact analysis | Bhupinder | 100% | 2020-03-16 | 2020-03-16
| RFQ Training and planning | Akshay | 100% | 2020-03-18 | 2020-03-18
| Website elements | Harjot | 100% | 2020-03-18 | 2020-03-18
| Maintenance cost structure | Harjot | 100% | 2020-03-17 | 2020-03-17
| Medical Imaging Marketing Group's Website ideas. | Devangi | 100% | 2020-03-14 | 2020-03-14
| TrackR App Upgrade Team Website Ideas | Harjot | 100% | 2020-03-14 | 2020-03-14
| ITBA Team Website Suggestions | Akshay | 100% | 2020-03-14 | 2020-03-14
| First draft of a Corporate Website | Harjot | 100% | 2020-03-15 | 2020-03-15
| Annotated List of Elements in Excel Sheet | Suneel | 100% | 2020-03-17 | 2020-03-17
| User Interface and Other Standards | Bhupinder | 100% | 2020-03-17 | 2020-03-17
| Website Elements Cost Estimating Excel Worksheet(s) and Workbook | Suneel | 100% | 2020-03-18 | 2020-03-18
| Request for Quotation for Website Developer Services | Akshay | 100% | 2020-03-18 | 2020-03-18
| Detailed Project Plan | Devangi | 100% | 2020-03-18 | 2020-03-18
| Training plan for 3 executives on Website Tech and uses | Devangi | 100% | 2020-03-19 | 2020-03-19
| Risks of Using Website to sell or support TrackRs. | Devangi | 100% | 2020-03-19 | 2020-03-19
| Metric(s) to determine the impact of the website. | Devangi | 100% | 2020-03-20 | 2020-03-20
11.7 | Update project scope | Devangi | 100% | 2020-03-13 | 2020-03-13
E. Requests For Information from Client
12 | Develop Initial RFI Content | Harjot | 100% | 2020-02-24 | 2020-02-27
12.1 | Prepare RFI #1 Document and Submit | Suneel | 100% | 2020-02-28 | 2020-02-28
12.2 | Review and Process Received Answers | All Team members | 100% | 2020-03-05 | 2020-03-05
F. Presentation Elements
13 | Prepare presentation content | All Team members | 20% | 2020-03-20 | 2020-03-25
13.1 | Create Powerpoint presentation | Harjot |  | 2020-03-23 | 2020-03-25
13.2 | Deliver Final Presentation | All Team members |  | 2020-03-26 | 2020-03-26
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About (hidden)
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.