## ReadMeFirst
INFO 8440 Team and Individual Time, Effort, Status Reporting Workbook
Created by: | Devangi Shah
History Table:
| Date | Version | Comments
| 2020 Feb 21 | 1 | Created and published
| 2020 Feb 22 | 2 | Added Actual RACI Columns, and Task Types
Sheets
ReadMeFirst | This sheet. Gives an overview of the entire workbook
RACI | The latest version of the RACI for the team for this project.
2020 Feb 21 | The RACI sheet as of Feb 21 at start of class.
Devangi Shah | The Daily Time log for Devangi Shah
Harjot Singh | The Daily Time log for Harjot Singh
Suneel Maurya | The Daily Time log for Suneel Maurya
Akshaykumar Pendam | The Daily Time log for Akshaykumar Pendam
Bhupinder Singh | The Daily Time log for Bhupinder Singh

## 21-Feb-20 (hidden)
Team Task Planning and Assignment Worksheet
Project Team: |  |  | Team 2
Date : |  |  | 2020-02-21
|  |  |  | Shah,Devangi | Singh,Harjot | Maurya,Suneel | Pendam,Akshay Kumar | Singh,Bhupinder | [6 empty] | Shah,Devangi ( Project Manager) | Singh,Harjot (Program Manager) | Maurya,Suneel | Pendam,Akshay Kumar | Singh,Bhupinder
Deliverable |  | Activity/Task (VERB: Subject) |  | RACI - PLAN |  |  |  |  | Due Date (M/D/Y) | Projected Effort (person - hrs) | Task Type - Team, Single or SubTeam | Task Version | Actual Start Date (M/D/Y) | Done On Date (M/D/Y) | RACI - ACTUAL
A | Project Management Plan
|  | 1 | Develop overall Project Management Plan | R,A | R | I | I | I |  |  | SubTeam |  |  |  | R,A | R | I | I | I
|  | 1.1 | Prepare Project Planning Document | R,A | R | I | I | I |  |  | Single |  |  |  | R,A | R | I | I | I
B | Tools
|  | 2 | Develop RACL Version 1 Chart Spreadsheet | R,A | R | I | I | I |  |  | Single |  |  |  | R,A | R | I | I | I
|  | 2.1 | Develop RACL Version 1 Content | R,A | R | C | C | C |  |  | Team |  |  |  | R,A | R | C | C | C
|  |  |  | R,A | [10 empty] | R,A
|  | 3 | Develop Team Contract Content | R,A | R | R | C | C |  |  | Team |  |  |  | R,A | R | R | C | C
|  | 3.1 | Prepare Team Contract Document | R,A | R | I | I | R |  |  | Single |  |  |  | R,A | R | I | I | R
C | Project Documentation
|  | 4 | Develop Project Scope Content | R,A | R | R | R | R |  |  | Team
|  | 4.1 | Prepare Project Scope Document | R,A | R | I | I | I |  |  | Single
|  |  | Element 1: Client Background | R,A | R | I | I | I |  |  | Single
|  | 4.2 | CDL Background & History | R,A | R | I | I | I |  |  | Single
|  | 4.3 | Stakeholder List and description | R,A | R | I | I | I |  |  | Single
|  | 4.4 | Current CDL business challenges | R,A | R | C | I | I |  |  | Team
|  | 4.5 | List of Brands Involved | R,A | R | I | I | I |  |  | Single
|  |  | Element 2: Scope | R,A | I | C | I | I |  |  | Team
|  |  | Element 3: Tools and Techniques | R,A | I | I | C | I |  |  | Team
|  | 5 | Work breakdown structure | R,A | R | C | I | I |  |  | SubTeam
|  | 5.1 | Gantt Chart | R,A | R | C | I | I |  |  | Single
|  |  | Element 4: Considerations | R,A | R | I | C | I |  |  | Single
|  | 6 | Risk List | R,A | R | I | C | I |  |  | Single
|  | 6.1 | Style Guide for Application | R,A | R | I | I | C |  |  | Single
|  | 6.2 | Project Team Performance | R,A | R | I | I | I |  |  | Single
|  | 6.3 | RFI Assumptions | R,A | I | I | I | I |  |  | Single
|  |  | Element 5: Report Components Content | R,A | I | I | I | C |  |  | Team
|  | 7 | Cover Letter | R,A | I | I | I | C |  |  | Single
|  | 7.1 | Cover Page | R,A | I | I | I | C |  |  | Single
|  | 7.2 | Document History Chart | R,A | I | I | I | C |  |  | Single
|  | 7.3 | TOC | R,A | I | I | I | C |  |  | Single
|  | 7.4 | Document Formatting | R,A | I | I | I | C |  |  | Single
|  |  | Element 6: Submission Quality | R,A | R,A | R | R | R |  |  | SubTeam
|  | 8 | Deliver Project Mngt Plan Package | R,A | R | I | I | I |  |  | Team
|  | 9 | Update RACI and Publish | R,A | C | C | C | C |  |  | Team
|  | 9.1 | Update RACI and Publish | R,A | C | C | C | C |  |  | Team
|  | 9.2 | Update RACI and Publish | R,A | C | C | C | C |  |  | Team
|  | 9.3 | Update RACI and Publish | R,A | C | C | C | C |  |  | Team
|  | 10 | Submit Final RACI to eConestoga |  | R,A | [5 empty] | Single
|  | 3.2 | Update Team Contract Content | R,A | C | C | C | R |  |  | Team
|  | 4.6 | Prepare Ver 2 Team Contract Document | R,A | I | I | I | R |  |  | Single
|  | 4.7 | Update Project Scope Content | R,A | R | R | R | R |  |  | Single
|  | 4.8 | Prepare Ver 2 Project Scope Document | R,A | R | I | I | I |  |  | Single
|  | 1.2 | Deliver Ver 2 Project Mngt Plan Package | R,A | R | I | I | I |  |  | Team
D | Submission Element
|  | 9.1 | History of CDL | R,A | I | C | I | I |  |  | Single
|  | 9.2 | List and descriptions of actors/ stakeholders | R,A | I | C | I | I |  |  | Single
|  | 9.3 | As-Is Principles of CDL | R,A | I | C | I | I |  |  | Single
|  | 9.4 | Current business challenges of CDL | R,A | I | C | I | I |  |  | Single
|  | 10.1 | Gifts, skills,attitudes of actors/stakeholders | R,A | I | I | C | I |  |  | Single
|  | 10.2 | Implementation strategy | R,A | C | I | I | I |  |  | Single
|  | 10.3 | Agile methodology | R,A | C | I | I | I |  |  | Single
|  | 10.4 | Develop Use Cases Contents | R,A | I | I | C | R |  |  | Team
|  | 10.5 | Prepare Use Case diagram | R,A | R | I | C | I |  |  | Single
|  | 10.6 | Cockburn template for each interaction | R,A | I | I | I | C |  |  | Single
|  | 11.1 | Current website screens and its functional documentation | R,A | R | I | I | C |  |  | Team
|  | 11.2 | Identified flaws or issues | R,A | I | I | C | I |  |  | Single
|  | 11.3 | The known client requirements | R,A | I | I | C | I |  |  | Single
|  | 11.4 | build prototype and navigation | R,A | I | I | C | I |  |  | Single
|  | 11.5 | Prototype content | R,A | C | I | I | R |  |  | Team
|  | 11.6 | Annotating prototype | R,A | C | I | I | I |  |  | Single
|  | 11.7 | Menumap creation | R,A | I | I | I | C |  |  | Single
|  | 11.8 | Functional documentation | R,A | C | I | I | I |  |  | Single
|  | 12.1 | As-Is process flow | R,A | C | I | I | I |  |  | Single
|  | 12.2 | To-be process flow | R,A | I | I | I | I |  |  | Single
|  | 12.3 | Job descriptions of Website devlopers | R,A | I | I | I | C |  |  | Single
|  | 12.4 | Project budget | R,A | I | I | I | C |  |  | Team
|  | 12.5 | End users and customers- definition | R,A | I | I | I | C |  |  | Single
|  | 12.6 | Brief list of risks and benefits associated with the website creation | R,A | I | I | I | R |  |  | Single
|  | 12.7 | Metrics to determine website success or failure | R,A | I | I | I | R |  |  | Single
|  | 12.8 | Update project scope | R,A | C | C | C | C |  |  | Team
E | Presentation Elements
|  | 13 | Prepare presentation content | R,A | R | R | R | R |  |  | Team
|  | 13.1 | Create Powerpoint presentation | R,A | R | I | I | I |  |  | Single
|  | 13.2 | Deliver Final Presentation | R | R | R | R | R |  |  | Team
F | Verbal Status Reports to Instructor - Scrum Meetings
|  | 14 | Meeting 1- | R | R | R | R | R |  |  | Team
|  | 14.1 | Meeting 2- | R | R | R | R | R |  |  | Team
|  | 14.2 | Meeting 3- | R | R | R | R | R |  |  | Team
|  | 13.3 | Meeting 4- | R | R | R | R | R |  |  | Team
|  | 13.4 | Meeting 5- | R | R | R | R | R |  |  | Team
|  | 13.5 | Meeting 6- | R | R | R | R | R |  |  | Team
|  | 13.7 | Meeting 7- | R | R | R | R | R |  |  | Team

## 20 Mar 2020
Team Task Planning and Assignment Worksheet
Project Team: |  |  | Team 2
Date : |  |  | 2020-02-21
|  |  |  | Shah,Devangi ( Project Manager) | Singh,Harjot (Program Manager) | Maurya,Suneel Kumar | Pendam,Akshay Kumar | Singh,Bhupinder | [5 empty] | Shah,Devangi ( Project Manager) | Singh,Harjot (Program Manager) | Maurya,Suneel | Pendam,Akshay Kumar | Singh,Bhupinder
Deliverable |  | Activity/Task (VERB: Subject) |  | RACI - PLAN |  |  |  |  | Due Date (M/D/Y) | Projected Effort (person - hrs) | Task Type - Team, Single or SubTeam | Actual Start Date (M/D/Y) | Done On Date (M/D/Y) | RACI - ACTUAL
A | Project Management Plan
|  | 1 | Develop overall Project Management Plan | R,A | R | I | I | I | 2020-02-20 | 1 | SubTeam | 2020-02-20 | 2020-02-20
|  | 1.1 | Prepare Project Planning Document | R,A | R | I | I | I | 2020-02-21 | 1 | Single | 2020-02-21 | 2020-02-21
B | Tools
|  | 2 | Develop RACL Version 1 Chart Spreadsheet | R,A | R | I | I | I | 2020-02-21 | 1 | Single | 2020-02-21 | 2020-02-21
|  | 2.1 | Develop RACL Version 1 Content | R,A | R | C | C | C | 2020-02-21 | 2 | Team | 2020-02-21 | 2020-02-21
|  | 3 | Develop Team Contract Content | R,A | R | R | C | C | 2020-02-21 | 1 | Team | 2020-02-21 | 2020-02-21 | A,C | C | C | C | R
|  | 3.1 | Prepare Team Contract Document | R,A | R | I | I | R | 2020-02-21 | 1 | Single | 2020-02-21 | 2020-02-22 | A,C | C | C | C | R
C | Project Documentation
|  | 4 | Develop Project Scope Content | A,C | C | R | C | C | 2020-02-21 | 2 | Team | 2020-02-21 | 2020-02-24
|  | 4.1 | Prepare Project Scope Document | A,C | C | R | C | C | 2020-02-25 | 1 | Single | 2020-02-25 | 2020-02-25
|  |  | Element 1: Client Background | A | R | I | I | I | 2020-02-25 | 1 | Single | 2020-02-25 | 2020-02-25
|  | 4.2 | CDL Background & History | R,A | I | I | I | I | 2020-02-25 | 1 | Single | 2020-02-25 | 2020-02-25 | A | R | I | I | I
|  | 4.3 | Stakeholder List and description | A | I | I | I | R | 2020-02-25 | 1 | Single | 2020-02-25 | 2020-02-25 | A | R | I | I | R
|  | 4.4 | Current CDL business challenges | A | C | C | R | I | 2020-02-25 | 2 | Team | 2020-02-25 | 2020-02-25 | A | R | C | I | I
|  | 4.5 | List of Brands Involved | A | I | R | I | I | 2020-02-26 | 1 | Single | 2020-02-26 | 2020-02-26 | A | R | I | I | I
|  |  | Element 2: Scope | R,A | C | C | C | C | 2020-02-26 | 1 | Team | 2020-02-26 | 2020-02-29 | R,A | R | R | C | C
|  |  | Element 3: Tools and Techniques | R,A | I | I | C | I | 2020-02-26 | 1 | Team | 2020-02-28 | 2020-03-01
|  | 5 | Work breakdown structure | A | C | R | I | I | 2020-02-23 | 1 | SubTeam | 2020-02-25 | 2020-02-27
|  | 5.1 | Gantt Chart | R,A | R | C | I | I | 2020-03-04 | 1 | Single | 2020-03-04 | 2020-03-04
|  |  | Element 4: Considerations | R,A | R | I | C | I | 2020-03-04 | 1 | Single | 2020-03-04 | 2020-03-04
|  | 6 | Risk List | R,A | R | I | C | I | 2020-03-04 | 0.5 | Single | 2020-03-04 | 2020-03-04
|  | 6.1 | Style Guide for Application | R,A | R | I | I | C | 2020-03-04 | 1 | Single | 2020-03-04 | 2020-03-04
|  | 6.2 | Project Team Performance | A | R | C | I | I | 2020-03-04 | 1 | Single | 2020-03-04 | 2020-03-04
|  | 6.3 | Assumptions | R,A | I | I | C | I | 2020-03-04 | 0.25 | Single | 2020-03-04 | 2020-03-04
|  |  | Element 5: Report Components Content | R,A | I | I | I | C | 2020-03-04 | 1 | Team | 2020-03-04 | 2020-03-04
|  | 7 | Cover Letter | A | R | I | I | I | 2020-03-06 | 0.25 | Single | 2020-03-06 | 2020-03-06
|  | 7.1 | Cover Page | A | I | R | I | I | 2020-03-06 | 1 | Single | 2020-03-06 | 2020-03-06
|  | 7.2 | Document History Chart | A | I | R | C | C | 2020-03-06 | 0.25 | Single | 2020-03-06 | 2020-03-06
|  | 7.3 | TOC | A | I | R | I | I | 2020-03-06 | 2 | Single | 2020-03-06 | 2020-03-06
|  | 7.4 | Document Formatting | A | C | R | I | I | 2020-03-06 | 0.5 | Single | 2020-03-06 | 2020-03-06
|  |  | Element 6: Submission Quality | R,A | R,A | R | R | R | 2020-03-06 | 0.5 | SubTeam | 2020-03-06 | 2020-03-06
D | Submission Element
|  | 8 | History of CDL | R,A | C | C | C | C | 2020-02-25 | 2 | Team | 2020-02-25 | 2020-02-25
|  | 8.1 | List and descriptions of actors/ stakeholders | R,A | C | C | C | C | 2020-02-25 | 2 | Team | 2020-02-25 | 2020-02-25
|  | 8.2 | As-Is Principles of CDL | R,A | C | C | C | C | 2020-02-25 | 2 | Team | 2020-02-25 | 2020-02-25
|  | 8.3 | Current business challenges of CDL | R,A | I | C | I | I | 2020-02-25 | 1 | Single | 2020-02-25 | 2020-02-25
|  | 9 | Gifts, skills,attitudes of actors/stakeholders | R,A | C | C | C | R | 2020-02-26 | 1 | Team | 2020-02-26 | 2020-02-26
|  | 9.1 | Implementation strategy | A | I | I | I | R | 2020-02-26 | 2 | Single | 2020-02-26 | 2020-02-26
|  | 9.2 | Agile methodology | R,A | R | R | R | R | 2020-02-26 | 1 | Single | 2020-02-26 | 2020-02-26
|  | 9.3 | Develop Use Cases Contents | A | R | C | I | I | 2020-02-27 | 1 | Single | 2020-02-27 | 2020-02-27
|  | 9.4 | Prepare Use Case diagram | A | R | C | I | I | 2020-02-27 | 1 | Team | 2020-02-27 | 2020-02-27
|  | 9.5 | Cockburn template for each interaction | R,A | I | I | C | I | 2020-02-27 | 1 | SubTeam | 2020-02-27 | 2020-02-27
|  | 10 | Current app screens and its functional documentation | A,C | C | I | R | I | 2020-03-17 | 0.5 | SubTeam | 2020-03-17 | 2020-03-17
|  | 10.1 | Identified flaws or issues | A | C | C | R | I | 2020-03-11 | 1 | Single | 2020-03-11 | 2020-03-11
|  | 10.2 | The known client requirements | A | I | R | I | I | 2020-03-11 | 1 | Single | 2020-03-11 | 2020-03-11
|  | 10.3 | Build prototype and navigation | A,C | R | R | C | C | 2020-03-12 | 1 | Single | 2020-03-12 | 2020-03-12
|  | 10.4 | Prototype Content | R,A | R | C | I | I | 2020-03-13 | 1 | Single | 2020-03-13 | 2020-03-13
|  | 10.5 | Annotating prototype | A | I | I | R | I | 2020-03-14 | 1 | Single | 2020-03-14 | 2020-03-14
|  | 10.6 | Menumap creation | A | C | R | I | I | 2020-03-15 | 1 | Single | 2020-03-15 | 2020-03-15
|  | 10.7 | Functional documentation | A | C | I | I | R | 2020-03-18 | 1 | Single | 2020-03-18 | 2020-03-18
|  | 10.8 | Create pseudocode | R,A | I | I | C | R | 2020-03-18 | 2 | Team | 2020-03-18 | 2020-03-18
|  | 10.9 | Valiate and update changes in pseudocode | R,A | R | I | C | I | 2020-03-18 | 1 | Single | 2020-03-18 | 2020-03-18
|  | 11 | As-Is process flow | A | I | I | I | R | 2020-03-18 | 0.5 | Single | 2020-03-18 | 2020-03-18
|  | 11.1 | To-be process flow | A,C | R | C | C | C | 2020-03-19 | 1 | Team | 2020-03-19 | 2020-03-19
|  | 11.2 | Job descriptions of Website devlopers | A | I | R | I | I | 2020-03-19 | 1 | Single | 2020-03-19 | 2020-03-19
|  | 11.3 | Project budget | R,A | C | C | C | C | 2020-03-20 | 1 | Single | 2020-03-20 | 2020-03-20
|  | 11.4 | End users and customers- definition | A | R | R | C | I | 2020-03-20 | 1 | Single | 2020-03-20 | 2020-03-20
|  | 11.5 | Brief list of risks and benefits associated with the website creation | R,A | C | I | I | R | 2020-03-20 | 1 | Team | 2020-03-20 | 2020-03-20
|  | 11.6 | Metrics to determine website success or failure | A | C | I | R | I | 2020-03-20 | 0.5 | Single | 2020-03-20 | 2020-03-20
|  | 11.7 | Update project scope | R,A | C | C | C | C | 2020-03-13 | 2 | Single | 2020-03-13 | 2020-03-13
|  | 11.8 | Risk analysis and Impact analysis | C | I | I | I | R,A | 2020-03-16 | 1 | Single | 2020-03-16 | 2020-03-16
|  | 11.9 | RFQ Training and planning | I | R | I | A,C | I | 2020-03-18 | 1 | Single | 2020-03-18 | 2020-03-18
|  | 12 | Website elements | I | R | A,C | I | I | 2020-03-18 | 1 | Single | 2020-03-18 | 2020-03-18
|  | 12.1 | Maintenance cost structure | I | R | A,C | I | I | 2020-03-17 | 1 | Single | 2020-03-17 | 2020-03-17
|  | 13 | Medical Imaging Marketing Group's Website ideas. | R,A | I | I | I | C | 2020-03-14 | 1 | Single | 2020-03-14 | 2020-03-14
|  | 13.1 | TrackR App Upgrade Team Website Ideas | C | R,A | I | I | I | 2020-03-14 | 1 | Single | 2020-03-14 | 2020-03-14
|  | 13.2 | ITBA Team Website Suggestions | I | I | C | R,A | I | 2020-03-14 | 1 | SubTeam | 2020-03-14 | 2020-03-14
|  | 13.3 | First draft of a Corporate Website | I | R | A,C | I | I | 2020-03-15 | 1 | Single | 2020-03-15 | 2020-03-15
|  | 13.4 | Annotated List of Elements in Excel Sheet | A,C | I | R | I | I | 2020-03-17 | 1 | Team | 2020-03-17 | 2020-03-17
|  | 13.5 | User Interface and Other Standards | I | I | I | C | R,A | 2020-03-17 | 1 | Team | 2020-03-17 | 2020-03-17
|  | 13.6 | Website Elements Cost Estimating Excel Worksheet(s) and Workbook | I | A,C | R | I | I | 2020-03-18 | 1 | Team | 2020-03-18 | 2020-03-18
|  | 13.7 | Request for Quotation for Website Developer Services | I | I | C | R,A | I | 2020-03-18 | 1 | Single | 2020-03-18 | 2020-03-18
|  | 13.8 | Detailed Project Plan | R,A | C | I | I | I | 2020-03-18 | 0.5 | Single | 2020-03-18 | 2020-03-18
|  | 13.9 | Training plan for 3 executives on Website Tech and uses | R,A | I | C | I | I | 2020-03-19 | 1 | Single | 2020-03-19 | 2020-03-19
|  | 14 | Risks of Using Website to sell or support TrackRs. | R,A | I | I | I | C | 2020-03-19 | 1 | Single | 2020-03-19 | 2020-03-19
|  | 14.1 | Metric(s) to determine the impact of the website. | R,A | I | I | C | I | 2020-03-20 | 1 | Single | 2020-03-20 | 2020-03-20
E | Requests For Information from Client
|  | 12 | Develop Initial RFI Content | A,C | R | C | C | C | 2020-02-27 | 2 | Team | 2020-02-24 | 2020-02-27
|  | 12.1 | Prepare RFI #1 Document and Submit | A | I | R | I | I | 2020-02-27 | 2 | Single | 2020-02-28 | 2020-02-28
|  | 12.2 | Review and Process Received Answers | R | R | R | R | R | 2020-02-28 | 1 | Team | 2020-03-05 | 2020-03-05
F | Presentation Elements
|  | 13 | Prepare presentation content | R,A | R | R | R | R | 2020-03-25 |  | Team
|  | 13.1 | Create Powerpoint presentation | R,A | R | I | I | I | 2020-03-25 |  | Single
|  | 13.2 | Deliver Final Presentation | R,A | R | R | R | R | 2020-03-25 |  | Team
G | Verbal Status Reports to Instructor - Scrum Meetings
|  | 14 | Meeting 1- Discussed what we have done, are doing,and will do next | R | R | R | R | R | 2020-02-27 |  | Team | 2020-02-27 | 2020-02-27
|  | 14.1 | Meeting 2-Discussed what we have done, are doing,and will do next | R | R | R | R | R | 2020-02-28 |  | Team | 2020-02-28 | 2020-02-28 | R | R | Abs | R | R
|  | 14.2 | Meeting 3- Discussed about the project solutions approach | R | R | R | R | R | 2020-03-04 |  | Team | 2020-03-04 | 2020-03-04 | R | R | R | Abs | R
|  | 14.3 | Meeting 4- Discussed about RFI answers | R | R | R | R | R | 2020-03-05 |  | Team | 2020-03-05 | 2020-03-05 | R | Abs | R | R | R
|  | 14.4 | Meeting 5- Had discussion with Subject Matter expert | R | R | R | R | R | 2020-03-06 |  | Team | 2020-03-06 | 2020-03-06
|  | 14.5 | Meeting 6- Discussed about project scope and how to improve | R | R | R | R | R | 2020-03-11 |  | Team | 2020-03-11 | 2020-03-11 | R | Abs | R | R | R
|  | 14.6 | Meeting 7- Discussed about the survey | R | R | R | R | R | 2020-03-18 |  | Team | 2020-03-18 | 2020-03-18
|  | 14.7 | Meeting 8- Discussed about the current and future state being assigned to each member | R | R | R | R | R | 2020-03-19 |  | Team | 2020-03-19 | 2020-03-19
|  | 14.8 | Meeting 9 - Discussed about the final documentation | R | R | R | R | R | 2020-03-20 |  | Team | 2020-03-20 | 2020-03-20
H | Other Research work
|  | 15 | Suggestion about elicitation techniques from team members | R | R | R | R | R | 2020-03-09 |  | Team | 2020-03-09 | 2020-03-09
|  | 15.1 | Research about cost regarding upgrade on website | R | R | R | R | R | 2020-03-11 |  | Team | 2020-03-11 | 2020-03-11
|  | 15.2 | Creating Forms | R | R | R | R | R | 2020-03-12 |  | Team | 2020-03-12 | 2020-03-12 | R | Abs | R | R | R
|  | 15.3 | Additional RFI | R | R | R | R | R | 2020-03-12 |  | Team | 2020-03-12 | 2020-03-12
|  | 15.4 | Survey Implementation | R | R | R | R | R | 2020-03-13 |  | Team | 2020-03-13 | 2020-03-13
|  | 15.5 | Survey ideas and suggestions | R | R | R | R | R | 2020-03-13 |  | Team | 2020-03-13 | 2020-03-13

## Devangi Shah
Devangi Shah Time Tracking
|  |  | Plan | (hrs) | Actual | (hrs)
RowID | Date | ActivityID | StartTime | Duration | StartTime | Duration | EndTime | Complete% | Comments
1 | 2020-02-21 | 1 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 20%
2 | 2020-02-25 | 2 | 16:30 | 0.5 | 16:00 | 0.91667 | 16:55 | 20%
3 | 2020-02-25 | 4 | 15:00 | 1 | 15:00 | 0.75 | 15:45 | 20%
5 | 2020-02-26 | 6 | 13:15 | 0.5 | 13:25 | 0.58333 | 14:00 | 35%
6 | 2020-03-06 | 7 | 15:00 | 0.5 | 14:55 | 0.41667 | 15:20 | 50%
7 | 2020-03-06 | 8 | 13:30 | 0.5 | 13:20 | 0.33333 | 13:40 | 15%
8 | 2020-03-11 | 13 | 15:00 | 1 | 15:00 | 0.75 | 15:45 | 20%
9 | 2020-03-18 | 14 | 13:15 | 0.5 | 13:25 | 0.58333 | 14:00 | 35%

## Harjot Singh
Harjot Singh Time Tracking
|  |  | Plan | (hrs) | Actual | (hrs)
RowID | Date | ActivityID | StartTime | Duration | StartTime | Duration | EndTime | Complete% | Comments
1 | 2020-02-21 | 2 | 13:30 | 0.5 | 13:20 | 0.33333 | 13:40 | 100%
2 | 2020-02-26 | 3 | 13:30 | 2 | 13:45 | 1.75 | 15:30 | 100%
3 | 2020-02-25 | 4 | 12:15 | 0.5 | 12:25 | 0.33333 | 12:45 | 50%
4 | 2020-02-27 | 7 | 12:15 | 0.5 | 17:00 | 3.75 | 20:45 | 100%
5 | 2020-03-06 | 8 | 15:00 | 1 | 15:00 | 0.75 | 15:45 | 20%
6 | 2020-03-06 | 9 | 13:15 | 0.5 | 13:25 | 0.58333 | 14:00 | 35%
7 | 2020-03-11 | 11 | 15:00 | 1 | 15:00 | 0.75 | 15:45 | 60%
8 | 2020-03-17 | 12 | 12:15 | 0.5 | 12:25 | 0.33333 | 12:45 | 50%

## Suneel Maurya
Suneel Maurya Time Tracking
|  |  | Plan | (hrs) | Actual | (hrs)
RowID | Date | ActivityID | StartTime | Duration | StartTime | Duration | EndTime | Complete% | Comments
1 | 2020-02-21 | 2 | 20:00 | 0.5 | 20:00 | 0.91667 | 20:55 | 100%
2 | 2020-02-21 | 3 | 20:00 | 0.5 | 20:00 | 0.5 | 20:30 | 100%
3 | 2020-02-25 | 6 | 20:00 | 2 | 20:00 | 1 | 21:00 | 35%
4 | 2020-02-26 | 7 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 60%
5 | 2020-03-04 | 8 | 13:30 | 0.5 | 13:00 | 0.91667 | 13:55 | 60%
6 | 2020-03-05 | 9 | 15:00 | 1 | 15:00 | 0.75 | 15:45 | 60%
7 | 2020-03-11 | 10 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 60%
8 | 2020-03-18 | 13 | 20:00 | 0.5 | 20:00 | 0.91667 | 20:55 | 100%

## Akshaykumar Pendam
Akshaykumar Pendam Time Tracking
|  |  | Plan | (hrs) | Actual | (hrs)
RowID | Date | ActivityID | StartTime | Duration | StartTime | Duration | EndTime | Complete% | Comments
1 | 2020-02-21 | 2 | 20:00 | 0.5 | 20:00 | 0.91667 | 20:55 | 50%
2 | 2020-02-25 | 3 | 20:00 | 0.5 | 20:00 | 0.5 | 20:30 | 100%
3 | 2020-02-25 | 7 | 12:15 | 0.5 | 12:25 | 0.58333 | 13:00 | 100%
4 | 2020-02-26 | 8 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 100%
5 | 2020-03-05 | 9 | 13:30 | 0.5 | 13:20 | 0.33333 | 13:40 | 100%
6 | 2020-03-12 | 11 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 100%
7 | 2020-03-13 | 14 | 12:15 | 0.5 | 12:25 | 0.58333 | 13:00 | 100%

## Bhupinder Singh
Bhupinder Singh Time Tracking
|  |  | Plan | (hrs) | Actual | (hrs)
RowID | Date | ActivityID | StartTime | Duration | StartTime | Duration | EndTime | Complete% | Comments
1 | 2020-02-21 | 1 | 12:15 | 0.5 | 12:25 | 0.33333 | 12:45 | 100%
2 | 2020-02-21 | 2 | 12:15 | 0.5 | 17:00 | 3.75 | 20:45 | 35%
3 | 2020-02-28 | 3 | 12:15 | 0.5 | 12:25 | 0.58333 | 13:00 | 100%
4 | 2020-03-04 | 6 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 25%
5 | 2020-03-05 | 8 | 15:00 | 0.5 | 14:55 | 0.41667 | 15:20 | 50%
6 | 2020-03-06 | 9 | 20:00 | 2 | 20:00 | 1 | 21:00 | 35%
7 | 2020-03-17 | 13 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 25%