## Gantt Chart
Gantt Chart - Team1 | [7 empty] | Brijesh Patel BP Divjot Kaur DK Hyojin Ahn HA Sanket Batra SB Bhupinder Singh BS
Project3 - Production Inefficiency - INFO8440 - April 17th , 2020 | [10 empty] | Period Highlight: | 18 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
SB | BP | DK | HA | BS |  | ACTIVITY | PLAN START DAY | PLAN DURATION DAYS | ACTUAL START DAY | ACTUAL DURATION DAYS | PERCENT COMPLETE | Project Day
[12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
R | RA | R | R | R | 1 | Develop RFI Document | 1 | 8 | 1 | 8 | 100%
R | RA | R | R | R | 2 | Prepare Cover Letter | 1 | 8 | 1 | 8 | 100%
R | RA | R | R | R | 3 | Prepare Document history Chart | 1 | 8 | 1 | 8 | 100%
R | RA | R | R | R | 4 | Prepare Statement of Confidetiality | 1 | 8 | 1 | 9 | 100%
R | RA | R | R | R | 5 | Develop Executive Summery | 1 | 8 | 1 | 9 | 100%
R | RA | R | R | R | 6 | Develop Final RFI Document | 8 | 1 | 8 | 2 | 100%
A | R | C | C | C | 7 | Review and Submit the Final RFI Document | 8 | 1 | 8 | 2 | 100%
R | R | R | R | R | 8 | Review and Process Received Answers | 15 | 1 | 15 | 1 | 100%
A | R | C | C | C | 9 | RACI development | 8 | 28 | 8 | 9 | 50%
R | I | I | C | R | 10 | CDL History | 8 | 2 | 8 | 7 | 75%
R | I | I | C | R | 11 | Actors involved | 8 | 2 | 8 | 7 | 90%
R | RA | R | RC | RC | 12 | Current Challenges for CDL | 8 | 2 | 8 | 7 | 100%
R | RA | R | RC | RC | 13 | Project Scope | 8 | 2 | 8 | 7 | 100%
R | RA | R | RC | RC | 14 | Develop Work breakdown structure | 8 | 2 | 8 | 7 | 100%
R | RA | R | RC | RC | 15 | Develop Gantt Chart | 8 | 8 | 8 | 7 | 75%
R | RA | R | RC | RC | 16 | Team contract | 8 | 7 | 8 | 7 | 100%
R | RA | R | RC | RC | 17 | Team Structure | 8 | 7 | 8 | 8 | 100%
R | RA | R | RC | RC | 18 | Analyze AS IS Process of CDL | 15 | 0 | 15 | 1 | 90%
R | RA | R | RC | RC | 19 | Techniques for risk mitigation | 9 | 6 | 9 | 7 | 20%
C | R | R | C | C | 20 | Project Measures and Success | 9 | 7 | 9 | 7 | 35%
R | R | C | C | C | 21 | List of Assumptions | 9 | 7 | 9 | 7 | 55%
R | R | C | C | C | 22 | Collabaration of Document | 9 | 7 | 9 | 7 | 95%
R | R | R | R | R | 23 | Analyze To Be Process of CDL | 9 | 8 | 5 | 6 | 100%
R | R | R | R | R | 24 | Document To Be Process | 9 | 9 | 6 | 9 | 100%
R | R | R | R | R | 25 | Document important calculations into excel sheet | 9 | 7 | 6 | 9 | 90%
R | R | R | R | R | 26 | Document individual efforts into excel and word file | 9 | 7 | 6 | 9 | 95%