## ReadMeFirst
INFO 8440 Team and Individual Time, Effort, Status Reporting Workbook
Created by: | Sanket Batra
History Table:
| Date | Version | Comments
| 2020 Mar 29 | 1 | Created and published
| 2020 Mar 31 | 2 | Added Actual RACI Columns, and Task Types
| 2020 Apr 01 | 3 | Added Person Sheets, and Daily Report
| 2020 Apr 03 | 4 | Added As Is work distribution
| 2020 Apr 10 | 5 | Added to be work distribution
| 2020 Apr 17 | 6 | Added Presentation work distribution
Sheets
ReadMeFirst | This sheet. Gives an overview of the entire workbook
RACI | The latest version of the RACI for the team for this project
Week# | The RACI sheet as of that week
Sanket Batra | The Daily Time log for Sanket Batra
Brijesh Patel | The Daily Time log for Brijesh Patel
Divjot Kaur | The Daily Time log for Divjot Kaur
Bhupinder Singh | The Daily Time log for Bhupinder Singh
Hyojin Ahn | The Daily Time log for Hyojin Ahn

## RACI
Team Task Planning and Assignment Worksheet
Project Team : |  | Team 1
Date: |  | 2020-03-04
|  |  |  | Sanket Batra | Brijesh Patel | Divjot Kaur | Bhupinder Singh | Hyojin Ahn | [6 empty] | Sanket Batra (Project Manager) | Brijesh Patel (Program Manager) | Divjot Kaur | Bhupinder Singh | Hyojin Ahn
Deliverables |  | Activity/Task (VERB: Subject) |  | RACI - PLAN |  |  |  |  | Due Date (D/M/Y) | Projected Effort (person - hrs) | Task Type - Team, Single or SubTeam | Task Version | Actual Start Date (D/M/Y) | Done On Date (M/D/Y) | RACI - ACTUAL
A | Requests For Information from Client
|  | 1 | Develop Rough RFI Document | A | R | C | C | C | 2020-03-27 | 1 | Team |  | 2020-02-20 | 2020-02-27 | A | R | C | C | C
|  | 1.1 | Prepare Cover Letter | A | R | I | I | C | 2020-03-27 | 0.5 | Single |  | 2020-02-20 | 2020-02-27 | A | R | I | I | C
|  | 1.2 | Prepare Document history Chart | R | R | R | R | R | 2020-03-27 | 0.5 | Team |  | 2020-02-20 | 2020-02-27 | R | R | R | R | R
|  | 1.3 | Prepare Statement of Confidetiality | A | C | C | I | R | 2020-03-27 | 0.5 | Single |  | 2020-02-20 | 2020-02-28 | A | C | C | I | R
|  | 1.4 | Develop Executive Summery | A | C | R | C | C | 2020-03-27 | 0.5 | Team |  | 2020-02-20 | 2020-02-28 | A | C | R | C | C
|  | 1.5 | Develop Final RFI Document | A | C | R | C | C | 2020-03-27 | 1 | Single |  | 2020-02-27 | 2020-02-28 | A | C | R | C | C
|  | 1.6 | Review and Submit the Final RFI Document | A | R | C | C | C | 2020-03-27 | 0.5 | Single |  | 2020-02-27 | 2020-02-28 | A | R | C | C | C
|  | 1.7 | Review and Process Received Answers | R | R | R | R | R | 2020-04-01 | 2 | Team |  | 2020-03-05 | 2020-03-05 | R | R | R | R | R
B | PMP DOCUMENT
|  | 5 | Develop RACI | A,R | C | C | C | C | 2020-04-01 | 1 | Team |  | 2020-04-01 | 2020-04-01 | A,R | A,R | C | C | C
|  | 5.1 | History of CDL | R | I | I | I | I | 2020-04-01 | 0.5 | Team |  | 2020-04-01 | 2020-04-01 | R | R | I | I | I
|  | 5.2 | The involved Actors | R | I | I | C | I | 2020-04-01 | 0.5 | Team |  | 2020-04-01 | 2020-04-01 | R | R | I | I | C
|  | 5.3 | Challenges of CDL | C | R | C | I | R | 2020-04-01 | 0.5 | Team |  | 2020-04-01 | 2020-04-01 | C | C | R | C | I
|  | 5.4 | Project Scope | C | R | R | I | I | 2020-04-01 | 0.5 | Team |  | 2020-04-01 | 2020-04-01 | C | C | R | R | I
|  | 5.5 | Develop WBS | C | C | R,C | R | R | 2020-04-01 | 1 | Team |  | 2020-04-01 | 2020-04-01 | C | C | C | R,C | R
|  | 5.6 | Develop Gantt Chart | C | R | C | I | I | 2020-04-03 | 0.5 | Team |  | 2020-04-03 | 2020-04-03 | C | C | R | C | I
|  | 5.7 | Team contract | C | C | C,R | R | I | 2020-04-03 | 2 | Team |  | 2020-04-03 | 2020-04-03 | C | C | C | C,R | R
|  | 5.8 | Team Structure | A,R | R | C | C | C | 2020-04-03 | 1 | Team |  | 2020-04-03 | 2020-04-03 | A,R | A,R | R | C | C
|  | 5.9 | Analyze Risks | R | C | R | C | C | 2020-04-03 | 0.5 | Team |  | 2020-04-03 | 2020-04-03 | R | R | C | R | C
|  | 5.1 | Techniques of risk mitigation | R | R | I | I | I | 2020-04-03 | 0.5 | Team |  | 2020-04-03 | 2020-04-03 | R | R | R | I | I
|  | 5.11 | Project Measures and Success | C | R | R | C | C | 2020-04-03 | 0.5 | Team |  | 2020-04-03 | 2020-04-03 | C | C | R | R | C
|  | 5.12 | List of Assumptions | R | R | C | C | C | 2020-04-03 | 0.5 | Team |  | 2020-04-03 | 2020-04-03 | R | R | R | C | C
|  | 5.13 | Collabaration of Document | R | R | C | C | C | 2020-04-03 | 1 | Team |  | 2020-04-03 | 2020-04-03 | R | R | R | C | C
Research
|  | 8 | Research current technologies | R | R | R | R | R | 2020-04-02 | 1 | Team |  | 2020-03-25 | 2020-04-02 | R | R | R | R | R
|  | 8.1 | Research finance and cost | R | R | R | R | R | 2020-04-03 | 1 | Team |  | 2020-03-25 | 2020-04-03 | R | R | R | R | R
|  | 8.2 | Research future activities | R | R | R | R | R | 2020-03-08 | 1 | Team |  | 2020-03-25 | 2020-03-08 | R | R | R | R | R
As Is Identification
|  | 10 | Analyze the current state | R | R | R | R | R | 2020-04-02 | 1 | Team |  | 2020-03-25 | 2020-04-02 | R | R | R | R | R
|  | 10.1 | Document the current state | R | R | R | R | R | 2020-04-03 | 1 | Team |  | 2020-03-25 | 2020-04-03 | R | R | R | R | R
|  | 10.2 | Document the As Is calculation | R | R | R | R | R | 2020-03-08 | 1 | Team |  | 2020-03-25 | 2020-03-08 | R | R | R | R | R
To Be Suggestion
|  | 11 | Research the Future state | R | R | R | R | R | 2020-04-15 | 1 | Team |  | 2020-04-02 | 2020-04-17 | R | R | R | R | R
|  | 11.1 | Document the Future state | R | R | R | R | R | 2020-04-15 | 1 | Team |  | 2020-03-29 | 2020-04-17 | R | R | R | R | R
|  | 11.2 | Document the To Be calculation | R | R | R | R | R | 2020-03-15 | 1 | Team |  | 2020-03-29 | 2020-04-17 | R | R | R | R | R
|  | 11.3 | Siplace Automation | C | C | R | C | C | 2020-04-15 | 8 | Individual |  | 2020-04-03 | 2020-04-17 | C | C | R | C | C
|  | 11.4 | Six Sigma Techniques | C | C | C | R | C | 2020-04-15 | 8 | Individual |  | 2020-04-03 | 2020-04-17 | C | C | C | R | C
|  | 11.5 | Component Picking Sugestions | R | C | C | C | C | 2020-04-15 | 8 | Individual |  | 2020-04-03 | 2020-04-17 | R | C | C | C | C
|  | 11.6 | Assembling TrackR suggestion | C | R | C | C | C | 2020-04-15 | 8 | Individual |  | 2020-04-03 | 2020-04-17 | C | R | C | C | C
|  | 11.7 | Profit Loss and Staffing Calculations | C | C | C | C | R | 2020-04-15 | 8 | Individual |  | 2020-04-03 | 2020-04-17 | C | C | C | C | R
Verbal Status Reports to Instructor - Scrum Meetings
|  | 9.6 | Meeting - Dicussed with marketing VP | R | R | R | R | R | 2020-04-02 | 1 | Team |  | 2020-04-02 | 2020-04-02 | R | R | R | R | R
|  | 9.5 | Meeting - Dicussed regarding PMP deliverables | R | R | R | R | R | 2020-04-01 | 1 | Team |  | 2020-04-01 | 2020-04-01 | R | R | R | R | R
|  | 9.4 | Meeting - Discussed updates On RFI response and further work needs to be done | R | R | R | R | R | 2020-04-01 | 1 | Team |  | 2020-04-01 | 2020-04-01 | R | R | R | R | R
|  | 9.3 | Meeting - Request For Information to the client, Type and structure of the questions to be asked | R | R | R | R | R | 2020-03-26 | 1 | Team |  | 2020-03-26 | 2020-03-26 | R | R | R | R | R
|  | 9.2 | Meeting - Discussed updates on RFI document | R | R | R | R | R | 2020-03-27 | 1 | Team |  | 2020-03-27 | 2020-03-27 | R | R | R | R | R
|  | 9.1 | Meeting - Discussed about the Final Deliverable of RFI | R | R | R | R | R | 2020-03-28 | 1 | Team |  | 2020-03-28 | 2020-03-28 | R | R | R | R | R
|  | 9 | Meeting on Project 2 overview and Disscussion regarding RFI questions | R | R | R | R | R | 2020-03-21 | 0.5 | Team |  | 2020-03-21 | 2020-03-21 | R | R | R | R | R

## Week 3
Team Task Planning and Assignment Worksheet
Project Team : |  | Team 1
Date: |  | 2020-03-04
|  |  |  | Sanket Batra | Brijesh Patel | Divjot Kaur | Bhupinder Singh | Hyojin Ahn | [6 empty] | Sanket Batra (Project Manager) | Brijesh Patel (Program Manager) | Divjot Kaur | Bhupinder Singh | Hyojin Ahn
Deliverables |  | Activity/Task (VERB: Subject) |  | RACI - PLAN |  |  |  |  | Due Date (D/M/Y) | Projected Effort (person - hrs) | Task Type - Team, Single or SubTeam | Task Version | Actual Start Date (D/M/Y) | Done On Date (M/D/Y) | RACI - ACTUAL
A | Requests For Information from Client
|  | 1 | Develop Rough RFI Document | A | R | C | C | C | 2020-03-27 | 1 | Team |  | 2020-02-20 | 2020-02-27 | A | R | C | C | C
|  | 1.1 | Prepare Cover Letter | A | R | I | I | C | 2020-03-27 | 0.5 | Single |  | 2020-02-20 | 2020-02-27 | A | R | I | I | C
|  | 1.2 | Prepare Document history Chart | R | R | R | R | R | 2020-03-27 | 0.5 | Team |  | 2020-02-20 | 2020-02-27 | R | R | R | R | R
|  | 1.3 | Prepare Statement of Confidetiality | A | C | C | I | R | 2020-03-27 | 0.5 | Single |  | 2020-02-20 | 2020-02-28 | A | C | C | I | R
|  | 1.4 | Develop Executive Summery | A | C | R | C | C | 2020-03-27 | 0.5 | Team |  | 2020-02-20 | 2020-02-28 | A | C | R | C | C
|  | 1.5 | Develop Final RFI Document | A | C | R | C | C | 2020-03-27 | 1 | Single |  | 2020-02-27 | 2020-02-28 | A | C | R | C | C
|  | 1.6 | Review and Submit the Final RFI Document | A | R | C | C | C | 2020-03-27 | 0.5 | Single |  | 2020-02-27 | 2020-02-28 | A | R | C | C | C
|  | 1.7 | Review and Process Received Answers | R | R | R | R | R | 2020-04-01 | 2 | Team |  | 2020-03-05 | 2020-03-05 | R | R | R | R | R
B | PMP DOCUMENT
|  | 5 | Develop RACI | A,R | C | C | C | C | 2020-04-01 | 1 | Team |  | 2020-04-01 | 2020-04-01 | A,R | A,R | C | C | C
|  | 5.1 | History of CDL | R | I | I | I | I | 2020-04-01 | 0.5 | Team |  | 2020-04-01 | 2020-04-01 | R | R | I | I | I
|  | 5.2 | The involved Actors | R | I | I | C | I | 2020-04-01 | 0.5 | Team |  | 2020-04-01 | 2020-04-01 | R | R | I | I | C
|  | 5.3 | Challenges of CDL | C | R | C | I | R | 2020-04-01 | 0.5 | Team |  | 2020-04-01 | 2020-04-01 | C | C | R | C | I
|  | 5.4 | Project Scope | C | R | R | I | I | 2020-04-01 | 0.5 | Team |  | 2020-04-01 | 2020-04-01 | C | C | R | R | I
|  | 5.5 | Develop WBS | C | C | R,C | R | R | 2020-04-01 | 1 | Team |  | 2020-04-01 | 2020-04-01 | C | C | C | R,C | R
|  | 5.6 | Develop Gantt Chart | C | R | C | I | I | 2020-04-03 | 0.5 | Team |  | 2020-04-03 | 2020-04-03 | C | C | R | C | I
|  | 5.7 | Team contract | C | C | C,R | R | I | 2020-04-03 | 2 | Team |  | 2020-04-03 | 2020-04-03 | C | C | C | C,R | R
|  | 5.8 | Team Structure | A,R | R | C | C | C | 2020-04-03 | 1 | Team |  | 2020-04-03 | 2020-04-03 | A,R | A,R | R | C | C
|  | 5.9 | Analyze Risks | R | C | R | C | C | 2020-04-03 | 0.5 | Team |  | 2020-04-03 | 2020-04-03 | R | R | C | R | C
|  | 5.1 | Techniques of risk mitigation | R | R | I | I | I | 2020-04-03 | 0.5 | Team |  | 2020-04-03 | 2020-04-03 | R | R | R | I | I
|  | 5.11 | Project Measures and Success | C | R | R | C | C | 2020-04-03 | 0.5 | Team |  | 2020-04-03 | 2020-04-03 | C | C | R | R | C
|  | 5.12 | List of Assumptions | R | R | C | C | C | 2020-04-03 | 0.5 | Team |  | 2020-04-03 | 2020-04-03 | R | R | R | C | C
|  | 5.13 | Collabaration of Document | R | R | C | C | C | 2020-04-03 | 1 | Team |  | 2020-04-03 | 2020-04-03 | R | R | R | C | C
Research
|  | 8 | Research current technologies | R | R | R | R | R | 2020-04-02 | 1 | Team |  | 2020-03-25 | 2020-04-02 | R | R | R | R | R
|  | 8.1 | Research finance and cost | R | R | R | R | R | 2020-04-03 | 1 | Team |  | 2020-03-25 | 2020-04-03 | R | R | R | R | R
|  | 8.2 | Research future activities | R | R | R | R | R | 2020-03-08 | 1 | Team |  | 2020-03-25 | 2020-03-08 | R | R | R | R | R
As Is Identification
|  | 10 | Analyze the current state | R | R | R | R | R | 2020-04-02 | 1 | Team |  | 2020-03-25 | 2020-04-02 | R | R | R | R | R
|  | 10.1 | Document the current state | R | R | R | R | R | 2020-04-03 | 1 | Team |  | 2020-03-25 | 2020-04-03 | R | R | R | R | R
|  | 10.2 | Document the As Is calculation | R | R | R | R | R | 2020-03-08 | 1 | Team |  | 2020-03-25 | 2020-03-08 | R | R | R | R | R
To Be Suggestion
|  | 11 | Research the Future state | R | R | R | R | R | 2020-04-15 | 1 | Team |  | 2020-04-02 | 2020-04-17 | R | R | R | R | R
|  | 11.1 | Document the Future state | R | R | R | R | R | 2020-04-15 | 1 | Team |  | 2020-03-29 | 2020-04-17 | R | R | R | R | R
|  | 11.2 | Document the To Be calculation | R | R | R | R | R | 2020-03-15 | 1 | Team |  | 2020-03-29 | 2020-04-17 | R | R | R | R | R
|  | 11.3 | Siplace Automation | C | C | R | C | C | 2020-04-15 | 8 | Individual |  | 2020-04-03 | 2020-04-17 | C | C | R | C | C
|  | 11.4 | Six Sigma Techniques | C | C | C | R | C | 2020-04-15 | 8 | Individual |  | 2020-04-03 | 2020-04-17 | C | C | C | R | C
|  | 11.5 | Component Picking Sugestions | R | C | C | C | C | 2020-04-15 | 8 | Individual |  | 2020-04-03 | 2020-04-17 | R | C | C | C | C
|  | 11.6 | Assembling TrackR suggestion | C | R | C | C | C | 2020-04-15 | 8 | Individual |  | 2020-04-03 | 2020-04-17 | C | R | C | C | C
|  | 11.7 | Profit Loss and Staffing Calculations | C | C | C | C | R | 2020-04-15 | 8 | Individual |  | 2020-04-03 | 2020-04-17 | C | C | C | C | R
Verbal Status Reports to Instructor - Scrum Meetings
|  | 9.6 | Meeting - Dicussed with marketing VP | R | R | R | R | R | 2020-04-02 | 1 | Team |  | 2020-04-02 | 2020-04-02 | R | R | R | R | R
|  | 9.5 | Meeting - Dicussed regarding PMP deliverables | R | R | R | R | R | 2020-04-01 | 1 | Team |  | 2020-04-01 | 2020-04-01 | R | R | R | R | R
|  | 9.4 | Meeting - Discussed updates On RFI response and further work needs to be done | R | R | R | R | R | 2020-04-01 | 1 | Team |  | 2020-04-01 | 2020-04-01 | R | R | R | R | R
|  | 9.3 | Meeting - Request For Information to the client, Type and structure of the questions to be asked | R | R | R | R | R | 2020-03-26 | 1 | Team |  | 2020-03-26 | 2020-03-26 | R | R | R | R | R
|  | 9.2 | Meeting - Discussed updates on RFI document | R | R | R | R | R | 2020-03-27 | 1 | Team |  | 2020-03-27 | 2020-03-27 | R | R | R | R | R
|  | 9.1 | Meeting - Discussed about the Final Deliverable of RFI | R | R | R | R | R | 2020-03-28 | 1 | Team |  | 2020-03-28 | 2020-03-28 | R | R | R | R | R
|  | 9 | Meeting on Project 2 overview and Disscussion regarding RFI questions | R | R | R | R | R | 2020-03-21 | 0.5 | Team |  | 2020-03-21 | 2020-03-21 | R | R | R | R | R

## Week2
Team Task Planning and Assignment Worksheet
Project Team : |  | Team 1
Date: |  | 2020-04-01
|  |  |  | Sanket Batra | Brijesh Patel | Divjot Kaur | Bhupinder Singh | Hyojin Ahn | [6 empty] | Sanket Batra (Project Manager) | Brijesh Patel (Program Manager) | Divjot Kaur | Bhupinder Singh | Hyojin Ahn
Deliverables |  | Activity/Task (VERB: Subject) |  | RACI - PLAN |  |  |  |  | Due Date (M/D/Y) | Projected Effort (person - hrs) | Task Type - Team, Single or SubTeam | Task Version | Actual Start Date (M/D/Y) | Done On Date (M/D/Y) | RACI - ACTUAL
A | PMP DOCUMENT
|  | 5 | Develop RACI | A,R | C | C | C | C | 2020-04-01 |  | Team |  | 2020-04-01 | 2020-04-02 | A,R | C | C | C | C
|  | 5.1 | History of CDL | I | I | I | R | I | 2020-04-01 |  | Team |  | 2020-04-01 | 2020-04-02 | I | I | I | R | I
|  | 5.2 | The involved Actors | I | I | R | C | I | 2020-04-01 |  | Team |  | 2020-04-01 | 2020-04-02 | I | I | R | C | I
|  | 5.3 | Challenges of CDL | C | I | R | I | I | 2020-04-03 |  | Team |  | 2020-04-01 | 2020-04-02 | C | I | R | I | I
|  | 5.4 | Project Scope | R | R | C | C | R | 2020-04-03 |  | Team |  | 2020-04-01 | 2020-04-03 | R | R | C | C | R
|  | 5.5 | Develop WBS | C | C | C | R | C | 2020-04-03 |  | Team |  | 2020-04-01 | 2020-04-03 | C | C | C | R | C
|  | 5.6 | Develop Gantt Chart | C | R | C | I | I | 2020-04-03 |  | Team |  | 2020-04-01 | 2020-04-02 | C | R | C | I | I
|  | 5.7 | Team contract | C | C | I | R | I | 2020-04-03 |  | Team |  | 2020-04-01 | 2020-04-03 | C | C | I | R | I
|  | 5.8 | Team Structure | A,R | I | R | I | C | 2020-04-03 |  | Team |  | 2020-04-01 | 2020-04-03 | A | I | R | I | C
|  | 5.9 | Analyze Risks | I | C | I | C | R | 2020-04-03 |  | Team |  | 2020-04-01 | 2020-04-02 | I | C | I | C | R
|  | 5.1 | Techniques of risk mitigation | I | I | I | I | R | 2020-04-03 |  | Team |  | 2020-04-01 | 2020-04-02 | I | I | I | I | R
|  | 5.11 | Project Measures and Success | C | R | C | C | C | 2020-04-03 |  | Team |  | 2020-04-01 | 2020-04-03 | C | R | C | C | C
|  | 5.12 | List of Assumptions | C | R | I | I | I | 2020-04-03 |  | Team |  | 2020-04-01 | 2020-04-03 | C | R | I | I | I
|  | 5.13 | Collabaration of Document | R | R | C | C | C | 2020-04-03 |  | Team |  | 2020-04-01 | 2020-04-03 | R | R | C | C | C
Z |  | Verbal Status Reports to Instructor - Scrum Meetings
|  | 9.5 | Meeting - Dicussed regarding PMP deliverables | R | R | R | R | R | 2020-03-04 | 1 | Team |  | 2020-03-04 | 2020-03-04 | R | R | R | R | R
|  | 9.4 | Meeting - Discussed updates On RFI response and further work needs to be done | R | R | R | R | R | 2020-03-05 | 1 | Team |  | 2020-03-05 | 2020-03-05 | R | R | R | R | R
|  | 9.3 | Meeting - Request For Information to the client, Type and structure of the questions to be asked | R | R | R | R | R | 2020-02-26 | 1 | Team |  | 2020-02-26 | 2020-02-26 | R | R | R | R | R
|  | 9.2 | Meeting - Discussed updates on RFI document | R | R | R | R | R | 2020-02-27 | 1 | Team |  | 2020-02-27 | 2020-02-27 | R | R | R | R | R
|  | 9.1 | Meeting - Discussed about the Final Deliverable of RFI | R | R | R | R | R | 2020-02-28 | 1 | Team |  | 2020-02-28 | 2020-02-28 | R | R | R | R | R
|  | 9 | Meeting on Project 2 overview and Disscussion regarding RFI questions | R | R | R | R | R | 2020-02-20 | 0.5 | Team |  | 2020-02-20 | 2020-02-20 | R | R | R | R | R

## Week1
Team Task Planning and Assignment Worksheet
Project Team : |  |  | Team 1
Date: |  |  | 2020-03-26
|  |  |  | Sanket Batra | Brijesh Patel | Divjot Kaur | Bhupinder Singh | Hyojin Ahn | [6 empty] | Sanket Batra (Project Manager) | Brijesh Patel (Program Manager) | Divjot Kaur | Bhupinder Singh | Hyojin Ahn
Deliverables |  | Activity/Task (VERB: Subject) |  | RACI - PLAN |  |  |  |  | Due Date (M/D/Y) | Projected Effort (person - hrs) | Task Type - Team, Single or SubTeam | Task Version | Actual Start Date (M/D/Y) | Done On Date (M/D/Y) | RACI - ACTUAL
2020-03-28
A | Requests For Information from Client
|  | 1 | Develop Rough RFI Document | A | R | C | C | C |  | 1 | Team |  | 2020-03-26 | 2020-03-26 | A | R | C | C | C
|  | 1.1 | Prepare Cover Letter | A |  | R |  |  |  | 0.5 | Single |  | 2020-03-26 | 2020-03-26 | A |  | R
|  | 1.2 | Prepare Document history Chart | R | R | R | R | R |  | 0.5 | Team |  | 2020-03-27 | 2020-03-27 | R | R | R | R | R
|  | 1.3 | Prepare Statement of Confidetiality | C | C | C | I | R | [6 empty] | C | C | C | I | R
|  | 1.4 | Develop Executive Summery | A | C | R | C | C |  | 0.5 | TEam |  | 2020-03-26 | 2020-03-26 | A | C | R | C | C
|  | 1.5 | Develop Final RFI Document | A | R | I | C | C |  | 1 | Single |  | 2020-03-28 | 2020-03-28 | A | R | I | C | C
Z | Verbal Status Reports to Instructor - Scrum Meetings
|  | 9 | Meeting - Request For Information to the client, Type and structure of the questions to be asked | R | R | R | R | R | 2020-03-26 | 1 | Team |  | 2020-03-26 | 2020-03-26 | ED | R | R | R | R
|  | 9.1 | Meeting - Discussed updates on RFI document | R | R | R | R | R | 2020-03-27 | 1 | Team |  | 2020-03-27 | 2020-03-27
|  | 9.2 | Meeting - Discussed about the Final Deliverable of RFI | R | R | R | R | R | 2020-03-28 | 1 | Team |  | 2020-03-28 | 2020-03-28 | R | R | R | R | R
B | Waiting for / Preparing For ClassTime Meetings
|  | 3 | Meeting - Divided Work amongst Team of Reaserch regarding RFI | R | R | R | R | R | 2020-03-26 | 0.5 | Team |  | 2020-03-26 | 2020-03-26 | R | R | R | R | R
|  | 3.1 | Meeting - Group discussion on RFI questions | R | R | R | R | R | 2020-03-27 | 0.5 | Team |  | 2020-03-27 | 2020-03-27 | R | R | R | R | R
|  | 3.2 | Meeting - Finalizing the Final Document | R | R | R | R | R | 2020-03-28 | 0.5 | Team |  | 2020-03-28 | 2020-03-28 | R | R | R | R | R
C | Attending Lectures and Presentations
|  | 2 | Updated RACI | A | R | R | R | R | 2020-03-26 | 1 | Team |  | 2020-03-26 | 2020-03-26 | A | R | R | R | R
|  | 2.1 | Gathered Requirements | R | R | R | R | R | 2020-03-26 |  | Team |  | 2020-03-26 | 2020-03-26 | R | R | R | R | R
|  | 2.2 | Updated RACI | A | R | R | R | R | 2020-03-27 |  | Team |  | 2020-03-27 | 2020-03-27 | A | R | R | R | R
|  | 2.3 | Worked on RFI | R | R | R | R | R | 2020-03-27 |  | Team |  | 2020-03-27 | 2020-03-27 | R | R | R | R | R
|  | 2.4 | Updated RACI | A | R | R | R | R | 2020-03-28 |  | Team |  | 2020-03-28 | 2020-03-28 | A | R | R | R | R

## Sanket
Sanket Batra Time Tracking
|  |  | Plan | (hrs) | Actual | (hrs)
RowID | Date | ActivityID | StartTime | Duration | StartTime | Duration | EndTime | Complete% | Comments
5 | 2020-03-26 | 1.2 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 100%
6 | 2020-04-01 | 5 | 13:30 | 0.5 | 13:00 | 0.91667 | 13:55 | 100%
7 | 2020-04-01 | 5.4 | 15:00 | 2 | 15:00 | 0.75 | 15:45 | 100%
8 | 2020-04-02 | 5.8 |  | 0.5 |  | 0 |  | 100%
9 | 2020-04-02 | 5.13 | 12:15 | 0.5 | 12:25 | 0.58333 | 13:00 | 100%
8 | 2020-04-03 | 8.1 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 85%
8 | 2020-04-03 | 8.1 | 13:30 | 0.5 | 13:00 | 0.91667 | 13:55 | 70%
8 | 2020-04-10 | 8.2 | 15:00 | 2 | 15:00 | 0.75 | 15:45 | 75%
8 | 2020-04-10 | 8.2 |  | 0.5 |  | 0 |  | 75%
8 | 2020-04-10 | 8.2 | 12:15 | 0.5 | 12:25 | 0.58333 | 13:00 | 80%
10 | 2020-04-10 | 10 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 90%
10 | 2020-04-14 | 10.1 | 13:30 | 0.5 | 13:00 | 0.91667 | 13:55 | 95%
10 | 2020-04-15 | 10 | 15:00 | 2 | 15:00 | 0.75 | 15:45 | 100%
11 | 2020-04-16 | 11 |  | 0.5 |  | 0 |  | 100%
11 | 2020-04-16 | 11.1 | 12:15 | 0.5 | 12:25 | 0.58333 | 13:00 | 100%

## Brijesh
Brijesh Patel Time Tracking
|  |  | Plan | (hrs) | Actual | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | Duration | EndTime | Complete% | Comments
5 | 2020-03-26 | 1 | 12:15 | 0.5 | 12:25 | 0.58333 | 13:00 | 100%
6 | 2020-03-27 | 1.2 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 100%
7 | 2020-03-28 | 1.5 | 13:30 | 0.5 | 13:20 | 0.33333 | 13:40 | 100%
8 | 2020-04-01 | 5.4 | 13:30 | 2 | 13:20 | 0.33333 | 13:40 | 100%
9 | 2020-04-01 | 5.6 | 12:15 | 0.5 | 12:25 | 0.58333 | 13:00 | 100%
10 | 2020-04-01 | 5.11 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 100%
11 | 2020-04-03 | 5.12 | 13:30 | 0.5 | 13:20 | 0.33333 | 13:40 | 100%
12 | 2020-04-03 | 5.13 | 12:15 | 0.5 | 12:25 | 0.58333 | 13:00 | 100%
8 | 2020-04-03 | 8.1 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 100%
8 | 2020-04-03 | 8.1 | 13:30 | 0.5 | 13:00 | 0.91667 | 13:55 | 100%
8 | 2020-04-10 | 8.2 | 15:00 | 2 | 15:00 | 0.75 | 15:45 | 100%
8 | 2020-04-10 | 8.2 |  | 0.5 |  | 0 |  | 100%
8 | 2020-04-10 | 8.2 | 12:15 | 0.5 | 12:25 | 0.58333 | 13:00 | 100%
10 | 2020-04-10 | 10 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 85%
10 | 2020-04-14 | 10.1 | 13:30 | 0.5 | 13:00 | 0.91667 | 13:55 | 70%
10 | 2020-04-15 | 10 | 15:00 | 2 | 15:00 | 0.75 | 15:45 | 75%
11 | 2020-04-16 | 11 |  | 0.5 |  | 0 |  | 75%
11 | 2020-04-16 | 11.1 | 12:15 | 0.5 | 12:25 | 0.58333 | 13:00 | 80%

## Divjot
Divjot kaur Time Tracking
|  |  | Plan | (hrs) | Actual | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | Duration | EndTime | Complete% | Comments
5 | 2020-03-26 | 1.1 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 100%
6 | 2020-03-26 | 1.2 | 13:30 | 0.5 | 13:00 | 0.91667 | 13:55 | 100%
7 | 2020-03-26 | 1.3 | 15:00 | 2 | 15:00 | 0.75 | 15:45 | 100%
8 | 2020-03-26 | 1.4 | 20:00 | 0.5 | 20:00 | 0.75 | 20:45 | 100%
9 | 2020-04-01 | 5.2 | 20:00 | 0.5 | 20:00 | 0.91667 | 20:55 | 100%
10 | 2020-04-01 | 5.3 | 20:00 | 0.5 | 20:00 | 0.5 | 20:30 | 45%
11 | 2020-04-01 | 5.8 | 20:00 | 2 | 20:00 | 1 | 21:00 | 50%
8 | 2020-04-03 | 8.1 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 100%
8 | 2020-04-03 | 8.1 | 13:30 | 0.5 | 13:20 | 0.33333 | 13:40 | 100%
8 | 2020-04-10 | 8.2 | 13:30 | 2 | 13:20 | 0.33333 | 13:40 | 100%
8 | 2020-04-10 | 8.2 | 12:15 | 0.5 | 12:25 | 0.58333 | 13:00 | 100%
8 | 2020-04-10 | 8.2 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 100%
10 | 2020-04-10 | 10 | 13:30 | 0.5 | 13:20 | 0.33333 | 13:40 | 100%
10 | 2020-04-14 | 10.1 | 12:15 | 0.5 | 12:25 | 0.58333 | 13:00 | 100%
10 | 2020-04-15 | 10 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 100%
11 | 2020-04-16 | 11 | 13:30 | 0.5 | 13:00 | 0.91667 | 13:55 | 100%
11 | 2020-04-16 | 11.1 | 20:00 | 0.5 | 20:00 | 0.75 | 20:45 | 100%

## Bhupinder
Bhupinder Singh Time Tracking
|  |  | Plan | (hrs) | Actual | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | Duration | EndTime | Complete% | Comments
5 | 2020-03-27 | 1.2 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 100%
6 | 2020-04-02 | 5.1 | 13:30 | 0.5 | 13:20 | 0.33333 | 13:40 | 100%
7 | 2020-04-02 | 5.5 | 13:30 | 2 | 13:20 | 0.33333 | 13:40 | 100%
8 | 2020-04-02 | 5.7 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 100%
8 | 2020-04-03 | 8.1 | 20:00 | 0.5 | 20:00 | 0.75 | 20:45 | 100%
8 | 2020-04-03 | 8.1 | 20:00 | 0.5 | 20:00 | 0.91667 | 20:55 | 100%
8 | 2020-04-10 | 8.2 | 20:00 | 0.5 | 20:00 | 0.5 | 20:30 | 45%
8 | 2020-04-10 | 8.2 | 20:00 | 2 | 20:00 | 1 | 21:00 | 50%
8 | 2020-04-10 | 8.2 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 100%
10 | 2020-04-10 | 10 | 13:30 | 0.5 | 13:20 | 0.33333 | 13:40 | 100%
10 | 2020-04-14 | 10.1 | 13:30 | 2 | 13:20 | 0.33333 | 13:40 | 100%
10 | 2020-04-15 | 10 | 12:15 | 0.5 | 12:25 | 0.58333 | 13:00 | 100%
11 | 2020-04-16 | 11 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 100%
11 | 2020-04-16 | 11.1 | 13:30 | 0.5 | 13:20 | 0.33333 | 13:40 | 100%

## Hyojin
Hyojin Ahn Time Tracking
|  |  | Plan | (hrs) | Actual | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | Duration | EndTime | Complete% | Comments
5 | 2020-03-26 | 1.2 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 100%
6 | 2020-04-01 | 5.4 | 13:30 | 0.5 | 13:20 | 0.33333 | 13:40 | 100%
7 | 2020-04-01 | 5.9 | 13:30 | 1 | 13:45 | 1.75 | 15:30 | 100%
8 | 2020-04-01 | 5.1 | 12:15 | 0.5 | 12:25 | 0.91667 | 13:20 | 100%
8 | 2020-04-03 | 8.1 | 20:00 | 0.5 | 20:00 | 0.75 | 20:45 | 100%
8 | 2020-04-03 | 8.1 | 20:00 | 0.5 | 20:00 | 0.91667 | 20:55 | 100%
8 | 2020-04-10 | 8.2 | 20:00 | 0.5 | 20:00 | 0.5 | 20:30 | 45%
8 | 2020-04-10 | 8.2 | 20:00 | 2 | 20:00 | 1 | 21:00 | 50%
8 | 2020-04-10 | 8.2 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 100%
10 | 2020-04-10 | 10 | 13:30 | 0.5 | 13:20 | 0.33333 | 13:40 | 100%
10 | 2020-04-14 | 10.1 | 13:30 | 2 | 13:20 | 0.33333 | 13:40 | 100%
10 | 2020-04-15 | 10 | 12:15 | 0.5 | 12:25 | 0.58333 | 13:00 | 100%
11 | 2020-04-16 | 11 | 13:00 | 0.5 | 12:55 | 0.41667 | 13:20 | 100%
11 | 2020-04-16 | 11.1 | 13:30 | 0.5 | 13:20 | 0.33333 | 13:40 | 100%