## ReadMeFirst
INFO 8440 Team and Individual Time, Effort, Status Reporting Workbook
Created by: | Preethi Sowndharya Venkatesan
History Table:
| Date | Version | Comments
| 2020-01-30 | 1 | Created and published
Sheets
ReadMeFirst | This sheet. Gives an overview of the entire workbook
RACI | The latest version of the RACI for the team for this project. This sheet is cloned at the first of every class day, and then updated.
Gantt Chart | Gantt Chart for the project. All data on this sheet was taken from RACI
Person1 | The Daily Time log for Person1 of the Team. This is setup as an Excel list, and used by the DailyReport sheet. Always insert new lines at the base of the list, so that the message at the bottom always stays.
Person2 | The Daily Time log for Person2 of the Team.
Guidance:
1) | Update RACI data only in the RACI sheet!
2) | The Activity Numbers in the Person Sheets are the code number for the Activity from the RACI
3) | Teams will have to copy and update formulas in the Daily Report sheet, to create additional columns for team members
4) | The Daily Sheet for most teams should fit on one page, landscape.
5) | Formatting is left to you to do. This workbook is given to you as a guide. It must look different than this sample when submitted as INFO 8440 work.
6) | Save your work often. Save different versions of this file as backups.
7) | All dates must be formatted as DD-MMM or DD-MMM-YY 11-Jan-17 or 11-Jan
8) | The RACI-Actual Columns should only be filled in when the Actual differs from the Plan.
9) | On RACI network, each assignment as a special ID created by the principle deliverable or achievement (yellow lines), and a number on the furthest left corner of individual undertaking. For instance, thing A1 alludes to the main undertaking for the Request For Information deliverable
10) | Gantt Chart is created in Microsoft Project using the start and end date of each data

## RACI
Team Task Planning and Assignment Worksheet
Project Team: |  | Group 5
Date (Worksheet version): |  |  | 2020-01-30
|  |  |  | Preethi Sowndharya( Project Manager) | Bhupinder singh (Program Manager) | Sainam Mahi | Karan Nakrani | Harbir Singh | [7 empty] | Preethi sowndharya ( Project Manager) | Bhupinder Singh (Program Manager) | Sainam Mahi | Karan Nakrani | Harbir Singh
Code | Activity/Task (VERB: Subject) |  |  | RACI - PLAN |  |  |  |  | Due Date (D-M-Y) | Projected Effort (person - hrs) | Task Type - Team, Single or SubTeam | Task Version | Actual Start Date (D-M-Y) | Done On Date (D-M-Y) | WBS Phase | RACI - ACTUAL
A | Request For Information
1 | Make RFI base document |  |  | A | R | I | I | I | 2020-01-24 | 1:00 | Single | 1 | 2020-01-23 | 2020-01-23
2 | Create questions |  |  | R,A | R | R | R | R | 2020-01-24 | 1:00 | Team | 1 | 2020-01-23 | 2020-01-23
3 | Classify created questions |  |  | A | R | C | C | C | 2020-01-24 | 1:00 | Team | 1 | 2020-01-23 | 2020-01-23
4 | Compose cover letter |  |  | R,A | C | R | I | I | 2020-01-24 | 1:00 | Single | 1 | 2020-01-23 | 2020-01-23
5 | Compose executive summary |  |  | A | R | I | I | I | 2020-01-24 | 1:00 | Single | 1 | 2020-01-23 | 2020-01-23
6 | Compose Document History |  |  | A | R | I | I | I | 2020-01-24 | 1:00 | Single | 1 | 2020-01-23 | 2020-01-23
7 | Compose Satement of Confidentiality |  |  | A | R | R | I | I | 2020-01-24 | 1:00 | Single | 1 | 2020-01-23 | 2020-01-23
8 | Finish RFI document draft |  |  | A | R | I | I | I | 2020-01-24 | 1:00 | Single | 1 | 2020-01-23 | 2020-01-23
9 | Review RFI document draft |  |  | R,A | R | R | R | R | 2020-01-24 | 1:00 | Team | 1 | 2020-01-24 | 2020-01-24
10 | Prepare RFI document final version |  |  | R | A | C | C | C | 2020-01-24 | 1:00 | Team | 1 | 2020-01-24 | 2020-01-24
11 | Insert references |  |  | R | A | I | I | I | 2020-01-24 | 1:00 | Team | 1 | 2020-01-23 | 2020-01-24
12 | Submit RFI document ver. 1.0 |  |  | R, A | I | I | I | I | 2020-01-24 | 1:00 | Single | 1 | 2020-01-24 | 2020-01-24
13 | Examine answers received |  |  | R,A | R | R | R | R | 2020-01-30 | 1:00 | Team | 1 | 2020-01-30 | 2020-01-30
14 | Review feedback |  |  | R | R, A | R | R | R | 2020-01-30 | 1:00 | Team | 1 | 2020-01-31 | 2020-01-31
B | Project Management Documentation
1 | Make PM documentation base document |  |  | A | R | I | I | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-29 | 2020-01-29
2 | Compose cover letter |  |  | R | A | R | I | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
3 | Compose document history |  |  | A | R | I | I | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-29 | 2020-01-29
4 | Compose history of CDL |  |  | A | I | R | I | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
5 | Plan stakeholder Involved |  |  | A | I | R | R | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
6 | Explain CDL current business challenges involved |  |  | A | R | I | I | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
7 | List out the brands involved in CDL |  |  | A | I | R | I | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
8 | List key metrics of CDL |  |  | A | R | I | I | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
9 | Develop Project Scope |  |  | A | R | I | I | R | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
10 | Develop RACI matrix Chart document |  |  | A | R | I | C | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
11 | Prepare Gantt chart document |  |  | A | R | I | C | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
12 | Draw work breakdown structure document |  |  | A | R | I | I | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
14 | Prepare team contract and group structure |  |  | A | R | I | I | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
15 | List out and explain project considerations |  |  | A | R | I | I | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
16 | List out and explain project risks |  |  | R | A | I | R | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
17 | Prepare the style guide |  |  | R | A | I | C | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
18 | Describe team performance and project management |  |  | R | A | I | C | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
19 | List project measures of success |  |  | R | A | I | I | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
20 | List assumption list and description |  |  | R | A | I | I | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
21 | Finish project management document draft |  |  | A | R | C | I | C | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
22 | Review project management document draft |  |  | R | R | R | R | R | 2020-01-31 | 1:00 | Team | 1 | 2020-01-30 | 2020-01-31
23 | Prepare project management document final version |  |  | A | R | C | R | C | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
24 | Finish RACI matrix and Gantt chart document draft |  |  | A | R | I | R | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
25 | Review RACI matrix and Gantt chart draft |  |  | R | R, A | R | R | R | 2020-01-31 | 1:00 | Team | 1 | 2020-01-30 | 2020-01-31
26 | Prepare RACI matrix and Gantt chart final version |  |  | I | R, A | I | R | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
27 | Finish WBS document draft |  |  | A | R | I | R | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
28 | Review WBS document draft |  |  | R | R, A | R | R | R | 2020-01-31 | 1:00 | Team | 1 | 2020-01-30 | 2020-01-31
29 | Prepare WBS document final version |  |  | I | R, A | I | R | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
30 | Insert references |  |  | A | R | I | R | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
31 | Submit project management document ver. 1.0 |  |  | R, A | I | I | R | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
32 | Submit RACI matrix and Gantt chart ver. 1.0 |  |  | R, A | I | I | I | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
33 | Submit WBS document ver. 1.0 |  |  | R, A | I | I | R | I | 2020-01-31 | 1:00 | Single | 1 | 2020-01-30 | 2020-01-31
34 | Update RACI Chart on Weekly basis and Publish |  |  | C | R, A | C | C | C | 2020-02-07 | 1:00 | Single | 1 | 2020-02-07 | 2020-02-07
35 | Update RACI Chart on Weekly basis and Publish |  |  | C | R, A | C | C | C | 2020-02-14 | 1:00 | Single | 1 | 2020-02-14 | 2020-02-14
36 | Update RACI chart on Weekly basis and Publish |  |  | C | R, A | C | C | C | 2020-02-21 | 1:00 | Single | 1 | 2020-02-21 | 2020-02-21
37 | Update RACI chart on Weekly basis and Publish |  |  | C | R, A | C | C | C | 2020-02-28 | 1:00 | Single | 1 | 2020-02-28 | 2020-02-28
38 | Review feedback |  |  | R | R, A | R | I | R | 2020-02-04 | 1:00 | Single | 1 | 2020-02-06 | 2020-02-06
C | Strategy Report
1 | Make strategy report base document |  |  | A | R | I | I | I | 2020-02-14 | 1:00 | Single | 1 | 2020-02-06 | 2020-02-06
2 | Compose cover letter |  |  | R | A | I | I | I | 2020-02-14 | 1:00 | Single | 1 | 2020-02-07 | 2020-02-07
3 | Compose executive summary |  |  | A | R | I | I | I | 2020-02-14 | 1:00 | Single | 1 | 2020-02-07 | 2020-02-07
4 | Develop social media marketing strategy |  |  | R, A | R | R | I | R | 2020-02-14 | 3:00 | Team | 1 | 2020-02-13 | 2020-02-13
5 | Create social media marketing manager job description |  |  | A | I | R | I | I | 2020-02-14 | 1:00 | Single | 1 | 2020-02-13 | 2020-02-14
6 | Create social media marketer job description |  |  | A | I | R | I | I | 2020-02-14 | 1:00 | Single | 1 | 2020-02-13 | 2020-02-14
7 | Develop TrackR update strategy |  |  | A | I | I | R | I | 2020-02-14 | 3:00 | Team | 1 | 2020-02-13 | 2020-02-14
8 | Create TrackR prototype |  |  | A | R | I | R | I | 2020-02-14 | 4:00 | Single | 1 | 2020-02-13 | 2020-02-14
9 | Create as-is state for TrackR |  |  | A | R | I | I | I | 2020-02-14 | 3:00 | Single | 1 | 2020-02-13 | 2020-02-14
10 | Create to-be state for TrackR |  |  | A | R | I | I | I | 2020-02-14 | 3:00 | Single | 1 | 2020-02-13 | 2020-02-14
11 | Write agile development principles report |  |  | R | R,A | I | R | I | 2020-02-14 | 2:00 | Single | 1 | 2020-02-13 | 2020-02-14
12 | Draw use case diagrams |  |  | R | R,A | I | R | I | 2020-02-14 | 3:00 | Single | 1 | 2020-02-13 | 2020-02-14
13 | Detailed Project Plan for the social media marketers |  |  | R,A | R | I | I | I | 2020-02-14 | 1:00 | Single | 1 | 2020-02-13 | 2020-02-14
14 | Detailed Project Plan for the social media developers |  |  | A | R | I | I | I | 2020-02-14 | 1:00 | Single | 1 | 2020-02-13 | 2020-02-14
15 | Future Analysis and development activities |  |  | R,A | I | I | I | I | 2020-02-14 | 1:00 | Single | 1 | 2020-02-13 | 2020-02-14
14 | Finish strategy report document draft |  |  | R | R, A | R | I | R | 2020-02-14 | 1:00 | Team | 1 | 2020-02-13 | 2020-02-14
15 | Review strategy report document draft |  |  | I | R, A | I | I | I | 2020-02-14 | 1:00 | Single | 1 | 2020-02-13 | 2020-02-14
16 | Prepare strategy report document final version |  |  | A | R | I | C | I | 2020-02-14 | 1:00 | Single | 1 | 2020-02-13 | 2020-02-14
17 | Insert references |  |  | R, A | I | I | R | I | 2020-02-14 | 1:00 | Single | 1 | 2020-02-13 | 2020-02-14
18 | Submit strategy report document ver. 1.0 |  |  | I | I | A | I | R | 2020-02-14 | 1:00 | Single | 1 | 2020-02-13 | 2020-02-14
19 | Print strategy report document ver. 1.0 |  |  | R | R, A | R | R | R |  | 1:00 | Team | 1
20 | Review feedback
D | Presentation
1 | Develop presentation template |  |  | A | R | I | I | I | 2020-02-20 | 1:00 | Single | 1
2 | Filter important points from Strategy Report |  |  | R | R, A | R | I | R | 2020-02-20 | 2:00 | Team | 1
3 | Complete Powerpoint presentation draft |  |  | A | R | I | C | I | 2020-02-20 | 1:00 | Single | 1
4 | Verify Powerpoint presentation draft |  |  | R | R, A | R | I | R | 2020-02-14 | 1:00 | Team | 1
5 | Create references |  |  | A | R | I | I | I | 2020-02-20 | 1:00 | Single | 1
6 | Submit Powerpoint presentation |  |  | R, A | I | I | C | I | 2020-02-20 | 1:00 | Single | 1
7 | Presentation |  |  | R | R, A | R | R | R | 2020-02-21 | 0:35 | Team | 1
8 | Review feedback |  |  | R | R, A | R | R | R | 2020-01-30 | 1:00 | Team | 1
E | Scrum Meetings with Senior BA
1 | Scrum Meeting - kickoff |  |  | R,A | R | R | R | R | 2020-01-23 | 0:10 | Team | 1 | 2020-01-23 | 2020-01-23
2 | Review the given information |  |  | R,A | R | R | R | R | 2020-01-30 | 1:00 | Team | 1 | 2020-01-23 | 2020-01-23
3 | Srum Meeting - RFI draft evaluation |  |  | R,A | R | R | R | R | 2020-01-24 | 0:10 | Team | 1 | 2020-01-24 | 2020-01-24
4 | Review the given information |  |  | R,A | R | R | R | R | 2020-01-30 | 1:00 | Team | 1 | 2020-01-24 | 2020-01-24
5 | Scrum Meeting - Project 1 Management documentation guidance and orientation |  |  | R,A | R | R | R | R | 2020-01-30 | 0:10 | Team | 1 | 2020-01-30 | 2020-01-30
6 | Review the given information |  |  | R,A | R | R | R | R | 2020-01-30 | 1:00 | Team | 1 | 2020-01-30 | 2020-01-30
7 | Scrum Meeting-Project 1 Management documentation Status Report review |  |  | R,A | R | R | R | R | 2020-01-31 | 0:10 | Team | 1 | 2020-01-31 | 2020-01-31
8 | Review the given information |  |  | R,A | R | R | R | R | 2020-01-30 | 1:00 | Team | 1 | 2020-01-31 | 2020-01-31
9 | Scrum Meeting- Guidance and review on cover letter and raci chart |  |  | R,A | R | R | R | R | 2020-02-06 | 0:10 | Team | 1 | 2020-02-06 | 2020-02-06
10 | Review the given information |  |  | R,A | R | R | R | R | 2020-02-06 | 1:00 | Team | 1 | 2020-02-06 | 2020-02-06
11 | Scrum Meeting-Guidance for the preparation of Report Files |  |  | R,A | R | R | R | R | 2020-02-07 | 0:10 | Team | 1 | 2020-02-07 | 2020-02-07
12 | Review the given information |  |  | R,A | R | R | R | R | 2020-02-07 | 1:00 | Team | 1 | 2020-02-07 | 2020-02-07
13 | Scrum Meeting-Reporting the status of the Stratergy Report |  |  | R,A | R | R | R | R | 2020-02-13 | 0:10 | Team | 1 | 2020-02-13 | 2020-02-13
14 | Review the given information |  |  | R,A | R | R | R | R | 2020-02-13 | 1:00 | Team | 1 | 2020-02-13 | 2020-02-13
15 | Scrum Meeting-Reporting the complete status of the final stratergy Report |  |  | R,A | R | R | R | R | 2020-02-14 | 0:10 | Team | 1 | 2020-02-14 | 2020-02-14
16 | Review the given information |  |  | R,A | R | R | R | R | 2020-02-14 | 1:00 | Team | 1 | 2020-02-14 | 2020-02-14
17 | Scrum Meeting |  |  | R,A | R | R | R | R | 2020-02-20 | 0:10 | Team | 1 | 2020-02-20 | 2020-02-20
18 | Review the given information |  |  | R,A | R | R | R | R | 2020-02-20 | 1:00 | Team | 1 | 2020-02-20 | 2020-02-20
19 | Scrum Meeting |  |  | R,A | R | R | R | R | 2020-02-21 | 0:10 | Team | 1 | 2020-02-21 | 2020-02-21
20 | Review the given information |  |  | R,A | R | R | R | R | 2020-02-21 | 1:00 | Team | 1 | 2020-02-21 | 2020-02-21

## Preethi Sowndharya
Person 1 Time Tracking
|  |  | Plan | (hrs) | Actual | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | Duration | EndTime | Complete% | Comments
8 | 2020-01-23 | A1 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
9 | 2020-01-23 | A2 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
10 | 2020-01-23 | A3 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
11 | 2020-01-23 | A4 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
12 | 2020-01-23 | A5 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
13 | 2020-01-23 | A6 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
14 | 2020-01-23 | A7 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
15 | 2020-01-23 | A8 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
16 | 2020-01-24 | A9 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
17 | 2020-01-24 | A10 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
18 | 2020-01-24 | A11 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
19 | 2020-01-24 | A12 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
20 | 2020-01-30 | A13 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
21 | 2020-01-31 | A14 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
23 | 2020-01-29 | B1 | 8:00 | 1 | 8:15 | 1 | 9:15 | 100%
24 | 2020-01-30 | B2 | 8:00 | 1 | 8:15 | 0.41667 | 8:40 | 41.67%
24 | 2020-01-31 | B2 | 8:00 | 1 | 8:15 | 0.58333 | 8:50 | 58.33%
25 | 2020-01-29 | B3 | 8:00 | 1 | 8:15 | 1 | 9:15 | 100%
26 | 2020-01-30 | B4 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
26 | 2020-01-31 | B4 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
27 | 2020-01-30 | B5 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
27 | 2020-01-31 | B5 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
28 | 2020-01-30 | B6 | 8:00 | 1 | 8:15 | 0.56667 | 8:49 | 56.67%
28 | 2020-01-31 | B6 | 8:00 | 1 | 8:15 | 0.43333 | 8:41 | 43.33%
29 | 2020-01-30 | B7 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
29 | 2020-01-31 | B7 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
30 | 2020-01-30 | B8 | 8:00 | 1 | 8:15 | 0.83333 | 9:05 | 83.33%
30 | 2020-01-31 | B8 | 8:00 | 1 | 8:15 | 0.16667 | 8:25 | 16.67%
31 | 2020-01-30 | B9 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
31 | 2020-01-31 | B9 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
32 | 2020-01-30 | B10 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
32 | 2020-01-31 | B10 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
33 | 2020-01-30 | B11 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
33 | 2020-01-31 | B11 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
34 | 2020-01-30 | B12 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
34 | 2020-01-31 | B12 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
35 | 2020-01-30 | B13 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
35 | 2020-01-31 | B13 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
36 | 2020-01-30 | B14 | 8:00 | 1 | 8:15 | 0.2 | 8:27 | 20%
36 | 2020-01-31 | B14 | 8:00 | 1 | 8:15 | 0.8 | 9:03 | 80%
37 | 2020-01-30 | B15 | 8:00 | 1 | 8:15 | 0.2 | 8:27 | 20%
37 | 2020-01-31 | B15 | 8:00 | 1 | 8:15 | 0.8 | 9:03 | 80%
38 | 2020-01-30 | B16 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
38 | 2020-01-31 | B16 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
39 | 2020-01-30 | B17 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
39 | 2020-01-31 | B17 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
40 | 2020-01-30 | B18 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
40 | 2020-01-31 | B18 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
41 | 2020-01-30 | B19 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
41 | 2020-01-31 | B19 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
42 | 2020-01-30 | B20 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
42 | 2020-01-31 | B20 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
43 | 2020-01-30 | B21 | 8:00 | 1 | 8:15 | 0.58333 | 8:50 | 58.33%
43 | 2020-01-31 | B21 | 8:00 | 1 | 8:15 | 0.41667 | 8:40 | 41.67%
44 | 2020-01-30 | B22 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
44 | 2020-01-31 | B22 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
45 | 2020-01-30 | B23 | 8:00 | 1 | 8:15 | 0.6 | 8:51 | 60%
45 | 2020-01-31 | B23 | 8:00 | 1 | 8:15 | 0.4 | 8:39 | 40%
46 | 2020-01-30 | B24 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
46 | 2020-01-31 | B24 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
47 | 2020-01-30 | B25 | 8:00 | 1 | 8:15 | 0.6 | 8:51 | 60%
47 | 2020-01-31 | B25 | 8:00 | 1 | 8:15 | 0.4 | 8:39 | 40%
48 | 2020-01-30 | B26 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
48 | 2020-01-31 | B26 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
49 | 2020-01-30 | B27 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
49 | 2020-01-31 | B27 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
50 | 2020-01-30 | B28 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
50 | 2020-01-31 | B28 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
51 | 2020-01-30 | B29 | 8:00 | 1 | 8:10 | 0.33333 | 8:30 | 33.33%
51 | 2020-01-31 | B29 | 8:00 | 1 | 8:10 | 0.66667 | 8:50 | 66.67%
52 | 2020-01-30 | B30 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
52 | 2020-01-31 | B30 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
53 | 2020-01-30 | B31 | 8:00 | 1 | 8:10 | 0.75 | 8:55 | 75%
53 | 2020-01-31 | B31 | 8:00 | 1 | 8:10 | 0.25 | 8:25 | 25%
54 | 2020-01-30 | B32 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
54 | 2020-01-31 | B32 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
55 | 2020-02-07 | B33 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
56 | 2020-02-14 | B34 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
57 | 2020-02-21 | B35 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
58 | 2020-02-28 | B36 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
59 | 2020-02-06 | B37 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
61 | 2020-02-06 | C1 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
62 | 2020-02-07 | C2 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
63 | 2020-02-07 | C3 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
64 | 2020-02-13 | C4 | 8:00 | 3 | 8:30 | 1.9167 | 10:25 | 63.89%
64 | 2020-02-14 | C4 | 8:00 | 3 | 8:30 | 1.4167 | 9:55 | 47.22%
65 | 2020-02-13 | C5 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
65 | 2020-02-14 | C5 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
66 | 2020-02-13 | C6 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
66 | 2020-02-14 | C6 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
67 | 2020-02-13 | C7 | 8:00 | 3 | 8:30 | 1.8333 | 10:20 | 61.11%
67 | 2020-02-14 | C7 | 8:00 | 3 | 8:30 | 1.1667 | 9:40 | 38.89%
68 | 2020-02-13 | C8 | 8:00 | 4 | 8:30 | 2.3333 | 10:50 | 58.33%
68 | 2020-02-14 | C8 | 8:00 | 4 | 8:30 | 1.6667 | 10:10 | 41.67%
69 | 2020-02-13 | C9 | 8:00 | 3 | 8:30 | 2.5 | 11:00 | 83.33%
69 | 2020-02-14 | C9 | 8:00 | 3 | 8:30 | 0.5 | 9:00 | 16.67%
70 | 2020-02-13 | C10 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
70 | 2020-02-14 | C10 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
71 | 2020-02-13 | C11 | 8:00 | 2 | 8:30 | 1.4167 | 9:55 | 70.83%
71 | 2020-02-14 | C11 | 8:00 | 2 | 8:30 | 0.58333 | 9:05 | 29.17%
72 | 2020-02-13 | C12 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
72 | 2020-02-14 | C12 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
73 | 2020-02-13 | C13 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
73 | 2020-02-14 | C13 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
74 | 2020-02-13 | C14 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
74 | 2020-02-14 | C14 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
75 | 2020-02-13 | C15 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
75 | 2020-02-14 | C15 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
76 | 2020-02-13 | C16 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
76 | 2020-02-14 | C16 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
77 | 2020-02-13 | C17 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
77 | 2020-02-14 | C17 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
78 | 2020-02-13 | C18 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
78 | 2020-02-14 | C18 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
79 | 2020-02-13 | C19 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
79 |  | C19 |  | 1 |  | 1
80 |  | C20
84 | 2020-02-20 | D1 | 8:00 | 1 | 8:25 |  |  | 0%
85 | 2020-02-20 | D2 | 8:00 | 1 | 8:25 |  |  | 0%
86 | 2020-02-20 | D3 | 8:00 | 1 | 8:25 |  |  | 0%
87 | 2020-02-14 | D4 | 8:00 | 1 | 8:25 |  |  | 0%
88 | 2020-02-20 | D5 | 8:00 | 1 | 8:25 |  |  | 0%
89 | 2020-02-20 | D6 | 8:00 | 1 | 8:25 |  |  | 0%
90 | 2020-02-21 | D7 | 8:00 | 1 | 8:25 |  |  | 0%
91 | 2020-01-30 | D8 | 8:00 | 1 | 8:25 |  |  | 0%
93 | 2020-01-23 | E1 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
94 | 2020-01-30 | E2 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
95 | 2020-01-24 | E3 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
96 | 2020-01-30 | E4 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
97 | 2020-01-30 | E5 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
98 | 2020-01-30 | E6 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
99 | 2020-01-31 | E7 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
100 | 2020-01-30 | E8 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
101 | 2020-02-06 | E9 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
102 | 2020-02-06 | E10 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
103 | 2020-02-07 | E11 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
104 | 2020-02-07 | E12 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
105 | 2020-02-13 | E13 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
106 | 2020-02-13 | E14 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
107 | 2020-02-14 | E15 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
108 | 2020-02-14 | E16 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
109 | 2020-02-20 | E17 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
110 | 2020-02-20 | E18 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
111 | 2020-02-21 | E19 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
112 | 2020-02-21 | E20 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%

## Bhupinder singh
Person 2 Time Tracking
|  |  | Plan | (hrs) | Actual | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | Duration | EndTime | Complete% | Comments
8 | 2020-01-23 | A1 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
9 | 2020-01-23 | A2 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
10 | 2020-01-23 | A3 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
11 | 2020-01-23 | A4 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
12 | 2020-01-23 | A5 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
13 | 2020-01-23 | A6 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
14 | 2020-01-23 | A7 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
15 | 2020-01-23 | A8 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
16 | 2020-01-24 | A9 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
17 | 2020-01-24 | A10 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
18 | 2020-01-24 | A11 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
19 | 2020-01-24 | A12 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
20 | 2020-01-30 | A13 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
21 | 2020-01-31 | A14 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
23 | 2020-01-29 | B1 | 8:00 | 1 | 8:15 | 1 | 9:15 | 100%
24 | 2020-01-30 | B2 | 8:00 | 1 | 8:15 | 0.41667 | 8:40 | 41.67%
24 | 2020-01-31 | B2 | 8:00 | 1 | 8:15 | 0.58333 | 8:50 | 58.33%
25 | 2020-01-29 | B3 | 8:00 | 1 | 8:15 | 1 | 9:15 | 100%
26 | 2020-01-30 | B4 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
26 | 2020-01-31 | B4 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
27 | 2020-01-30 | B5 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
27 | 2020-01-31 | B5 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
28 | 2020-01-30 | B6 | 8:00 | 1 | 8:15 | 0.56667 | 8:49 | 56.67%
28 | 2020-01-31 | B6 | 8:00 | 1 | 8:15 | 0.43333 | 8:41 | 43.33%
29 | 2020-01-30 | B7 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
29 | 2020-01-31 | B7 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
30 | 2020-01-30 | B8 | 8:00 | 1 | 8:15 | 0.83333 | 9:05 | 83.33%
30 | 2020-01-31 | B8 | 8:00 | 1 | 8:15 | 0.16667 | 8:25 | 16.67%
31 | 2020-01-30 | B9 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
31 | 2020-01-31 | B9 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
32 | 2020-01-30 | B10 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
32 | 2020-01-31 | B10 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
33 | 2020-01-30 | B11 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
33 | 2020-01-31 | B11 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
34 | 2020-01-30 | B12 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
34 | 2020-01-31 | B12 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
35 | 2020-01-30 | B13 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
35 | 2020-01-31 | B13 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
36 | 2020-01-30 | B14 | 8:00 | 1 | 8:15 | 0.2 | 8:27 | 20%
36 | 2020-01-31 | B14 | 8:00 | 1 | 8:15 | 0.8 | 9:03 | 80%
37 | 2020-01-30 | B15 | 8:00 | 1 | 8:15 | 0.2 | 8:27 | 20%
37 | 2020-01-31 | B15 | 8:00 | 1 | 8:15 | 0.8 | 9:03 | 80%
38 | 2020-01-30 | B16 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
38 | 2020-01-31 | B16 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
39 | 2020-01-30 | B17 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
39 | 2020-01-31 | B17 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
40 | 2020-01-30 | B18 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
40 | 2020-01-31 | B18 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
41 | 2020-01-30 | B19 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
41 | 2020-01-31 | B19 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
42 | 2020-01-30 | B20 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
42 | 2020-01-31 | B20 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
43 | 2020-01-30 | B21 | 8:00 | 1 | 8:15 | 0.58333 | 8:50 | 58.33%
43 | 2020-01-31 | B21 | 8:00 | 1 | 8:15 | 0.41667 | 8:40 | 41.67%
44 | 2020-01-30 | B22 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
44 | 2020-01-31 | B22 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
45 | 2020-01-30 | B23 | 8:00 | 1 | 8:15 | 0.6 | 8:51 | 60%
45 | 2020-01-31 | B23 | 8:00 | 1 | 8:15 | 0.4 | 8:39 | 40%
46 | 2020-01-30 | B24 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
46 | 2020-01-31 | B24 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
47 | 2020-01-30 | B25 | 8:00 | 1 | 8:15 | 0.6 | 8:51 | 60%
47 | 2020-01-31 | B25 | 8:00 | 1 | 8:15 | 0.4 | 8:39 | 40%
48 | 2020-01-30 | B26 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
48 | 2020-01-31 | B26 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
49 | 2020-01-30 | B27 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
49 | 2020-01-31 | B27 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
50 | 2020-01-30 | B28 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
50 | 2020-01-31 | B28 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
51 | 2020-01-30 | B29 | 8:00 | 1 | 8:10 | 0.33333 | 8:30 | 33.33%
51 | 2020-01-31 | B29 | 8:00 | 1 | 8:10 | 0.66667 | 8:50 | 66.67%
52 | 2020-01-30 | B30 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
52 | 2020-01-31 | B30 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
53 | 2020-01-30 | B31 | 8:00 | 1 | 8:10 | 0.75 | 8:55 | 75%
53 | 2020-01-31 | B31 | 8:00 | 1 | 8:10 | 0.25 | 8:25 | 25%
54 | 2020-01-30 | B32 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
54 | 2020-01-31 | B32 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
55 | 2020-02-07 | B33 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
56 | 2020-02-14 | B34 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
57 | 2020-02-21 | B35 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
58 | 2020-02-28 | B36 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
59 | 2020-02-06 | B37 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
61 | 2020-02-06 | C1 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
62 | 2020-02-07 | C2 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
63 | 2020-02-07 | C3 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
64 | 2020-02-13 | C4 | 8:00 | 3 | 8:30 | 1.9167 | 10:25 | 63.89%
64 | 2020-02-14 | C4 | 8:00 | 3 | 8:30 | 1.4167 | 9:55 | 47.22%
65 | 2020-02-13 | C5 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
65 | 2020-02-14 | C5 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
66 | 2020-02-13 | C6 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
66 | 2020-02-14 | C6 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
67 | 2020-02-13 | C7 | 8:00 | 3 | 8:30 | 1.8333 | 10:20 | 61.11%
67 | 2020-02-14 | C7 | 8:00 | 3 | 8:30 | 1.1667 | 9:40 | 38.89%
68 | 2020-02-13 | C8 | 8:00 | 4 | 8:30 | 2.3333 | 10:50 | 58.33%
68 | 2020-02-14 | C8 | 8:00 | 4 | 8:30 | 1.6667 | 10:10 | 41.67%
69 | 2020-02-13 | C9 | 8:00 | 3 | 8:30 | 2.5 | 11:00 | 83.33%
69 | 2020-02-14 | C9 | 8:00 | 3 | 8:30 | 0.5 | 9:00 | 16.67%
70 | 2020-02-13 | C10 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
70 | 2020-02-14 | C10 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
71 | 2020-02-13 | C11 | 8:00 | 2 | 8:30 | 1.4167 | 9:55 | 70.83%
71 | 2020-02-14 | C11 | 8:00 | 2 | 8:30 | 0.58333 | 9:05 | 29.17%
72 | 2020-02-13 | C12 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
72 | 2020-02-14 | C12 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
73 | 2020-02-13 | C13 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
73 | 2020-02-14 | C13 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
74 | 2020-02-13 | C14 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
74 | 2020-02-14 | C14 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
75 | 2020-02-13 | C15 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
75 | 2020-02-14 | C15 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
76 | 2020-02-13 | C16 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
76 | 2020-02-14 | C16 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
77 | 2020-02-13 | C17 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
77 | 2020-02-14 | C17 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
78 | 2020-02-13 | C18 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
78 | 2020-02-14 | C18 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
79 | 2020-02-13 | C19 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
79 |  | C19 |  | 1 |  | 1
80 |  | C20
84 | 2020-02-20 | D1 | 8:00 | 1 | 8:25 |  |  | 0%
85 | 2020-02-20 | D2 | 8:00 | 1 | 8:25 |  |  | 0%
86 | 2020-02-20 | D3 | 8:00 | 1 | 8:25 |  |  | 0%
87 | 2020-02-14 | D4 | 8:00 | 1 | 8:25 |  |  | 0%
88 | 2020-02-20 | D5 | 8:00 | 1 | 8:25 |  |  | 0%
89 | 2020-02-20 | D6 | 8:00 | 1 | 8:25 |  |  | 0%
90 | 2020-02-21 | D7 | 8:00 | 1 | 8:25 |  |  | 0%
91 | 2020-01-30 | D8 | 8:00 | 1 | 8:25 |  |  | 0%
93 | 2020-01-23 | E1 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
94 | 2020-01-30 | E2 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
95 | 2020-01-24 | E3 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
96 | 2020-01-30 | E4 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
97 | 2020-01-30 | E5 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
98 | 2020-01-30 | E6 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
99 | 2020-01-31 | E7 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
100 | 2020-01-30 | E8 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
101 | 2020-02-06 | E9 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
102 | 2020-02-06 | E10 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
103 | 2020-02-07 | E11 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
104 | 2020-02-07 | E12 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
105 | 2020-02-13 | E13 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
106 | 2020-02-13 | E14 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
107 | 2020-02-14 | E15 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
108 | 2020-02-14 | E16 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
109 | 2020-02-20 | E17 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
110 | 2020-02-20 | E18 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
111 | 2020-02-21 | E19 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
112 | 2020-02-21 | E20 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%

## Sainam Mahi
Person 3 Time Tracking
|  |  | Plan | (hrs) | Actual | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | Duration | EndTime | Complete% | Comments
8 | 2020-01-23 | A1 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
9 | 2020-01-23 | A2 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
10 | 2020-01-23 | A3 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
11 | 2020-01-23 | A4 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
12 | 2020-01-23 | A5 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
13 | 2020-01-23 | A6 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
14 | 2020-01-23 | A7 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
15 | 2020-01-23 | A8 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
16 | 2020-01-24 | A9 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
17 | 2020-01-24 | A10 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
18 | 2020-01-24 | A11 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
19 | 2020-01-24 | A12 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
20 | 2020-01-30 | A13 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
21 | 2020-01-31 | A14 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
23 | 2020-01-29 | B1 | 8:00 | 1 | 8:15 | 1 | 9:15 | 100%
24 | 2020-01-30 | B2 | 8:00 | 1 | 8:15 | 0.41667 | 8:40 | 41.67%
24 | 2020-01-31 | B2 | 8:00 | 1 | 8:15 | 0.58333 | 8:50 | 58.33%
25 | 2020-01-29 | B3 | 8:00 | 1 | 8:15 | 1 | 9:15 | 100%
26 | 2020-01-30 | B4 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
26 | 2020-01-31 | B4 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
27 | 2020-01-30 | B5 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
27 | 2020-01-31 | B5 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
28 | 2020-01-30 | B6 | 8:00 | 1 | 8:15 | 0.56667 | 8:49 | 56.67%
28 | 2020-01-31 | B6 | 8:00 | 1 | 8:15 | 0.43333 | 8:41 | 43.33%
29 | 2020-01-30 | B7 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
29 | 2020-01-31 | B7 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
30 | 2020-01-30 | B8 | 8:00 | 1 | 8:15 | 0.83333 | 9:05 | 83.33%
30 | 2020-01-31 | B8 | 8:00 | 1 | 8:15 | 0.16667 | 8:25 | 16.67%
31 | 2020-01-30 | B9 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
31 | 2020-01-31 | B9 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
32 | 2020-01-30 | B10 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
32 | 2020-01-31 | B10 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
33 | 2020-01-30 | B11 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
33 | 2020-01-31 | B11 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
34 | 2020-01-30 | B12 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
34 | 2020-01-31 | B12 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
35 | 2020-01-30 | B13 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
35 | 2020-01-31 | B13 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
36 | 2020-01-30 | B14 | 8:00 | 1 | 8:15 | 0.2 | 8:27 | 20%
36 | 2020-01-31 | B14 | 8:00 | 1 | 8:15 | 0.8 | 9:03 | 80%
37 | 2020-01-30 | B15 | 8:00 | 1 | 8:15 | 0.2 | 8:27 | 20%
37 | 2020-01-31 | B15 | 8:00 | 1 | 8:15 | 0.8 | 9:03 | 80%
38 | 2020-01-30 | B16 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
38 | 2020-01-31 | B16 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
39 | 2020-01-30 | B17 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
39 | 2020-01-31 | B17 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
40 | 2020-01-30 | B18 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
40 | 2020-01-31 | B18 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
41 | 2020-01-30 | B19 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
41 | 2020-01-31 | B19 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
42 | 2020-01-30 | B20 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
42 | 2020-01-31 | B20 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
43 | 2020-01-30 | B21 | 8:00 | 1 | 8:15 | 0.58333 | 8:50 | 58.33%
43 | 2020-01-31 | B21 | 8:00 | 1 | 8:15 | 0.41667 | 8:40 | 41.67%
44 | 2020-01-30 | B22 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
44 | 2020-01-31 | B22 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
45 | 2020-01-30 | B23 | 8:00 | 1 | 8:15 | 0.6 | 8:51 | 60%
45 | 2020-01-31 | B23 | 8:00 | 1 | 8:15 | 0.4 | 8:39 | 40%
46 | 2020-01-30 | B24 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
46 | 2020-01-31 | B24 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
47 | 2020-01-30 | B25 | 8:00 | 1 | 8:15 | 0.6 | 8:51 | 60%
47 | 2020-01-31 | B25 | 8:00 | 1 | 8:15 | 0.4 | 8:39 | 40%
48 | 2020-01-30 | B26 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
48 | 2020-01-31 | B26 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
49 | 2020-01-30 | B27 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
49 | 2020-01-31 | B27 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
50 | 2020-01-30 | B28 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
50 | 2020-01-31 | B28 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
51 | 2020-01-30 | B29 | 8:00 | 1 | 8:10 | 0.33333 | 8:30 | 33.33%
51 | 2020-01-31 | B29 | 8:00 | 1 | 8:10 | 0.66667 | 8:50 | 66.67%
52 | 2020-01-30 | B30 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
52 | 2020-01-31 | B30 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
53 | 2020-01-30 | B31 | 8:00 | 1 | 8:10 | 0.75 | 8:55 | 75%
53 | 2020-01-31 | B31 | 8:00 | 1 | 8:10 | 0.25 | 8:25 | 25%
54 | 2020-01-30 | B32 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
54 | 2020-01-31 | B32 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
55 | 2020-02-07 | B33 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
56 | 2020-02-14 | B34 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
57 | 2020-02-21 | B35 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
58 | 2020-02-28 | B36 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
59 | 2020-02-06 | B37 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
61 | 2020-02-06 | C1 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
62 | 2020-02-07 | C2 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
63 | 2020-02-07 | C3 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
64 | 2020-02-13 | C4 | 8:00 | 3 | 8:30 | 1.9167 | 10:25 | 63.89%
64 | 2020-02-14 | C4 | 8:00 | 3 | 8:30 | 1.4167 | 9:55 | 47.22%
65 | 2020-02-13 | C5 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
65 | 2020-02-14 | C5 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
66 | 2020-02-13 | C6 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
66 | 2020-02-14 | C6 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
67 | 2020-02-13 | C7 | 8:00 | 3 | 8:30 | 1.8333 | 10:20 | 61.11%
67 | 2020-02-14 | C7 | 8:00 | 3 | 8:30 | 1.1667 | 9:40 | 38.89%
68 | 2020-02-13 | C8 | 8:00 | 4 | 8:30 | 2.3333 | 10:50 | 58.33%
68 | 2020-02-14 | C8 | 8:00 | 4 | 8:30 | 1.6667 | 10:10 | 41.67%
69 | 2020-02-13 | C9 | 8:00 | 3 | 8:30 | 2.5 | 11:00 | 83.33%
69 | 2020-02-14 | C9 | 8:00 | 3 | 8:30 | 0.5 | 9:00 | 16.67%
70 | 2020-02-13 | C10 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
70 | 2020-02-14 | C10 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
71 | 2020-02-13 | C11 | 8:00 | 2 | 8:30 | 1.4167 | 9:55 | 70.83%
71 | 2020-02-14 | C11 | 8:00 | 2 | 8:30 | 0.58333 | 9:05 | 29.17%
72 | 2020-02-13 | C12 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
72 | 2020-02-14 | C12 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
73 | 2020-02-13 | C13 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
73 | 2020-02-14 | C13 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
74 | 2020-02-13 | C14 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
74 | 2020-02-14 | C14 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
75 | 2020-02-13 | C15 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
75 | 2020-02-14 | C15 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
76 | 2020-02-13 | C16 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
76 | 2020-02-14 | C16 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
77 | 2020-02-13 | C17 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
77 | 2020-02-14 | C17 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
78 | 2020-02-13 | C18 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
78 | 2020-02-14 | C18 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
79 | 2020-02-13 | C19 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
79 |  | C19 |  | 1 |  | 1
80 |  | C20
84 | 2020-02-20 | D1 | 8:00 | 1 | 8:25 |  |  | 0%
85 | 2020-02-20 | D2 | 8:00 | 1 | 8:25 |  |  | 0%
86 | 2020-02-20 | D3 | 8:00 | 1 | 8:25 |  |  | 0%
87 | 2020-02-14 | D4 | 8:00 | 1 | 8:25 |  |  | 0%
88 | 2020-02-20 | D5 | 8:00 | 1 | 8:25 |  |  | 0%
89 | 2020-02-20 | D6 | 8:00 | 1 | 8:25 |  |  | 0%
90 | 2020-02-21 | D7 | 8:00 | 1 | 8:25 |  |  | 0%
91 | 2020-01-30 | D8 | 8:00 | 1 | 8:25 |  |  | 0%
93 | 2020-01-23 | E1 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
94 | 2020-01-30 | E2 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
95 | 2020-01-24 | E3 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
96 | 2020-01-30 | E4 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
97 | 2020-01-30 | E5 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
98 | 2020-01-30 | E6 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
99 | 2020-01-31 | E7 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
100 | 2020-01-30 | E8 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
101 | 2020-02-06 | E9 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
102 | 2020-02-06 | E10 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
103 | 2020-02-07 | E11 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
104 | 2020-02-07 | E12 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
105 | 2020-02-13 | E13 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
106 | 2020-02-13 | E14 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
107 | 2020-02-14 | E15 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
108 | 2020-02-14 | E16 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
109 | 2020-02-20 | E17 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
110 | 2020-02-20 | E18 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
111 | 2020-02-21 | E19 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
112 | 2020-02-21 | E20 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%

## Karan Nakrani
Person 4 Time Tracking
|  |  | Plan | (hrs) | Actual | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | Duration | EndTime | Complete% | Comments
8 | 2020-01-23 | A1 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
9 | 2020-01-23 | A2 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
10 | 2020-01-23 | A3 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
11 | 2020-01-23 | A4 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
12 | 2020-01-23 | A5 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
13 | 2020-01-23 | A6 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
14 | 2020-01-23 | A7 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
15 | 2020-01-23 | A8 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
16 | 2020-01-24 | A9 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
17 | 2020-01-24 | A10 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
18 | 2020-01-24 | A11 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
19 | 2020-01-24 | A12 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
20 | 2020-01-30 | A13 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
21 | 2020-01-31 | A14 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
23 | 2020-01-29 | B1 | 8:00 | 1 | 8:15 | 1 | 9:15 | 100%
24 | 2020-01-30 | B2 | 8:00 | 1 | 8:15 | 0.41667 | 8:40 | 41.67%
24 | 2020-01-31 | B2 | 8:00 | 1 | 8:15 | 0.58333 | 8:50 | 58.33%
25 | 2020-01-29 | B3 | 8:00 | 1 | 8:15 | 1 | 9:15 | 100%
26 | 2020-01-30 | B4 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
26 | 2020-01-31 | B4 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
27 | 2020-01-30 | B5 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
27 | 2020-01-31 | B5 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
28 | 2020-01-30 | B6 | 8:00 | 1 | 8:15 | 0.56667 | 8:49 | 56.67%
28 | 2020-01-31 | B6 | 8:00 | 1 | 8:15 | 0.43333 | 8:41 | 43.33%
29 | 2020-01-30 | B7 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
29 | 2020-01-31 | B7 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
30 | 2020-01-30 | B8 | 8:00 | 1 | 8:15 | 0.83333 | 9:05 | 83.33%
30 | 2020-01-31 | B8 | 8:00 | 1 | 8:15 | 0.16667 | 8:25 | 16.67%
31 | 2020-01-30 | B9 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
31 | 2020-01-31 | B9 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
32 | 2020-01-30 | B10 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
32 | 2020-01-31 | B10 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
33 | 2020-01-30 | B11 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
33 | 2020-01-31 | B11 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
34 | 2020-01-30 | B12 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
34 | 2020-01-31 | B12 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
35 | 2020-01-30 | B13 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
35 | 2020-01-31 | B13 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
36 | 2020-01-30 | B14 | 8:00 | 1 | 8:15 | 0.2 | 8:27 | 20%
36 | 2020-01-31 | B14 | 8:00 | 1 | 8:15 | 0.8 | 9:03 | 80%
37 | 2020-01-30 | B15 | 8:00 | 1 | 8:15 | 0.2 | 8:27 | 20%
37 | 2020-01-31 | B15 | 8:00 | 1 | 8:15 | 0.8 | 9:03 | 80%
38 | 2020-01-30 | B16 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
38 | 2020-01-31 | B16 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
39 | 2020-01-30 | B17 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
39 | 2020-01-31 | B17 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
40 | 2020-01-30 | B18 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
40 | 2020-01-31 | B18 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
41 | 2020-01-30 | B19 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
41 | 2020-01-31 | B19 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
42 | 2020-01-30 | B20 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
42 | 2020-01-31 | B20 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
43 | 2020-01-30 | B21 | 8:00 | 1 | 8:15 | 0.58333 | 8:50 | 58.33%
43 | 2020-01-31 | B21 | 8:00 | 1 | 8:15 | 0.41667 | 8:40 | 41.67%
44 | 2020-01-30 | B22 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
44 | 2020-01-31 | B22 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
45 | 2020-01-30 | B23 | 8:00 | 1 | 8:15 | 0.6 | 8:51 | 60%
45 | 2020-01-31 | B23 | 8:00 | 1 | 8:15 | 0.4 | 8:39 | 40%
46 | 2020-01-30 | B24 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
46 | 2020-01-31 | B24 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
47 | 2020-01-30 | B25 | 8:00 | 1 | 8:15 | 0.6 | 8:51 | 60%
47 | 2020-01-31 | B25 | 8:00 | 1 | 8:15 | 0.4 | 8:39 | 40%
48 | 2020-01-30 | B26 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
48 | 2020-01-31 | B26 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
49 | 2020-01-30 | B27 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
49 | 2020-01-31 | B27 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
50 | 2020-01-30 | B28 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
50 | 2020-01-31 | B28 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
51 | 2020-01-30 | B29 | 8:00 | 1 | 8:10 | 0.33333 | 8:30 | 33.33%
51 | 2020-01-31 | B29 | 8:00 | 1 | 8:10 | 0.66667 | 8:50 | 66.67%
52 | 2020-01-30 | B30 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
52 | 2020-01-31 | B30 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
53 | 2020-01-30 | B31 | 8:00 | 1 | 8:10 | 0.75 | 8:55 | 75%
53 | 2020-01-31 | B31 | 8:00 | 1 | 8:10 | 0.25 | 8:25 | 25%
54 | 2020-01-30 | B32 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
54 | 2020-01-31 | B32 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
55 | 2020-02-07 | B33 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
56 | 2020-02-14 | B34 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
57 | 2020-02-21 | B35 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
58 | 2020-02-28 | B36 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
59 | 2020-02-06 | B37 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
61 | 2020-02-06 | C1 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
62 | 2020-02-07 | C2 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
63 | 2020-02-07 | C3 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
64 | 2020-02-13 | C4 | 8:00 | 3 | 8:30 | 1.9167 | 10:25 | 63.89%
64 | 2020-02-14 | C4 | 8:00 | 3 | 8:30 | 1.4167 | 9:55 | 47.22%
65 | 2020-02-13 | C5 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
65 | 2020-02-14 | C5 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
66 | 2020-02-13 | C6 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
66 | 2020-02-14 | C6 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
67 | 2020-02-13 | C7 | 8:00 | 3 | 8:30 | 1.8333 | 10:20 | 61.11%
67 | 2020-02-14 | C7 | 8:00 | 3 | 8:30 | 1.1667 | 9:40 | 38.89%
68 | 2020-02-13 | C8 | 8:00 | 4 | 8:30 | 2.3333 | 10:50 | 58.33%
68 | 2020-02-14 | C8 | 8:00 | 4 | 8:30 | 1.6667 | 10:10 | 41.67%
69 | 2020-02-13 | C9 | 8:00 | 3 | 8:30 | 2.5 | 11:00 | 83.33%
69 | 2020-02-14 | C9 | 8:00 | 3 | 8:30 | 0.5 | 9:00 | 16.67%
70 | 2020-02-13 | C10 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
70 | 2020-02-14 | C10 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
71 | 2020-02-13 | C11 | 8:00 | 2 | 8:30 | 1.4167 | 9:55 | 70.83%
71 | 2020-02-14 | C11 | 8:00 | 2 | 8:30 | 0.58333 | 9:05 | 29.17%
72 | 2020-02-13 | C12 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
72 | 2020-02-14 | C12 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
73 | 2020-02-13 | C13 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
73 | 2020-02-14 | C13 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
74 | 2020-02-13 | C14 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
74 | 2020-02-14 | C14 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
75 | 2020-02-13 | C15 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
75 | 2020-02-14 | C15 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
76 | 2020-02-13 | C16 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
76 | 2020-02-14 | C16 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
77 | 2020-02-13 | C17 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
77 | 2020-02-14 | C17 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
78 | 2020-02-13 | C18 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
78 | 2020-02-14 | C18 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
79 | 2020-02-13 | C19 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
79 |  | C19 |  | 1 |  | 1
80 |  | C20
84 | 2020-02-20 | D1 | 8:00 | 1 | 8:25 |  |  | 0%
85 | 2020-02-20 | D2 | 8:00 | 1 | 8:25 |  |  | 0%
86 | 2020-02-20 | D3 | 8:00 | 1 | 8:25 |  |  | 0%
87 | 2020-02-14 | D4 | 8:00 | 1 | 8:25 |  |  | 0%
88 | 2020-02-20 | D5 | 8:00 | 1 | 8:25 |  |  | 0%
89 | 2020-02-20 | D6 | 8:00 | 1 | 8:25 |  |  | 0%
90 | 2020-02-21 | D7 | 8:00 | 1 | 8:25 |  |  | 0%
91 | 2020-01-30 | D8 | 8:00 | 1 | 8:25 |  |  | 0%
93 | 2020-01-23 | E1 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
94 | 2020-01-30 | E2 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
95 | 2020-01-24 | E3 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
96 | 2020-01-30 | E4 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
97 | 2020-01-30 | E5 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
98 | 2020-01-30 | E6 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
99 | 2020-01-31 | E7 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
100 | 2020-01-30 | E8 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
101 | 2020-02-06 | E9 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
102 | 2020-02-06 | E10 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
103 | 2020-02-07 | E11 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
104 | 2020-02-07 | E12 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
105 | 2020-02-13 | E13 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
106 | 2020-02-13 | E14 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
107 | 2020-02-14 | E15 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
108 | 2020-02-14 | E16 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
109 | 2020-02-20 | E17 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
110 | 2020-02-20 | E18 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
111 | 2020-02-21 | E19 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
112 | 2020-02-21 | E20 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%

## Harbir Singh
Person 5 Time Tracking
|  |  | Plan | (hrs) | Actual | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | Duration | EndTime | Complete% | Comments
8 | 2020-01-23 | A1 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
9 | 2020-01-23 | A2 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
10 | 2020-01-23 | A3 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
11 | 2020-01-23 | A4 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
12 | 2020-01-23 | A5 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
13 | 2020-01-23 | A6 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
14 | 2020-01-23 | A7 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
15 | 2020-01-23 | A8 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
16 | 2020-01-24 | A9 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
17 | 2020-01-24 | A10 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
18 | 2020-01-24 | A11 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
19 | 2020-01-24 | A12 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
20 | 2020-01-30 | A13 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
21 | 2020-01-31 | A14 | 8:00 | 1 | 8:05 | 1 | 9:05 | 100%
23 | 2020-01-29 | B1 | 8:00 | 1 | 8:15 | 1 | 9:15 | 100%
24 | 2020-01-30 | B2 | 8:00 | 1 | 8:15 | 0.41667 | 8:40 | 41.67%
24 | 2020-01-31 | B2 | 8:00 | 1 | 8:15 | 0.58333 | 8:50 | 58.33%
25 | 2020-01-29 | B3 | 8:00 | 1 | 8:15 | 1 | 9:15 | 100%
26 | 2020-01-30 | B4 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
26 | 2020-01-31 | B4 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
27 | 2020-01-30 | B5 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
27 | 2020-01-31 | B5 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
28 | 2020-01-30 | B6 | 8:00 | 1 | 8:15 | 0.56667 | 8:49 | 56.67%
28 | 2020-01-31 | B6 | 8:00 | 1 | 8:15 | 0.43333 | 8:41 | 43.33%
29 | 2020-01-30 | B7 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
29 | 2020-01-31 | B7 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
30 | 2020-01-30 | B8 | 8:00 | 1 | 8:15 | 0.83333 | 9:05 | 83.33%
30 | 2020-01-31 | B8 | 8:00 | 1 | 8:15 | 0.16667 | 8:25 | 16.67%
31 | 2020-01-30 | B9 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
31 | 2020-01-31 | B9 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
32 | 2020-01-30 | B10 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
32 | 2020-01-31 | B10 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
33 | 2020-01-30 | B11 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
33 | 2020-01-31 | B11 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
34 | 2020-01-30 | B12 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
34 | 2020-01-31 | B12 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
35 | 2020-01-30 | B13 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
35 | 2020-01-31 | B13 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
36 | 2020-01-30 | B14 | 8:00 | 1 | 8:15 | 0.2 | 8:27 | 20%
36 | 2020-01-31 | B14 | 8:00 | 1 | 8:15 | 0.8 | 9:03 | 80%
37 | 2020-01-30 | B15 | 8:00 | 1 | 8:15 | 0.2 | 8:27 | 20%
37 | 2020-01-31 | B15 | 8:00 | 1 | 8:15 | 0.8 | 9:03 | 80%
38 | 2020-01-30 | B16 | 8:00 | 1 | 8:15 | 0.66667 | 8:55 | 66.67%
38 | 2020-01-31 | B16 | 8:00 | 1 | 8:15 | 0.33333 | 8:35 | 33.33%
39 | 2020-01-30 | B17 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
39 | 2020-01-31 | B17 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
40 | 2020-01-30 | B18 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
40 | 2020-01-31 | B18 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
41 | 2020-01-30 | B19 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
41 | 2020-01-31 | B19 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
42 | 2020-01-30 | B20 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
42 | 2020-01-31 | B20 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
43 | 2020-01-30 | B21 | 8:00 | 1 | 8:15 | 0.58333 | 8:50 | 58.33%
43 | 2020-01-31 | B21 | 8:00 | 1 | 8:15 | 0.41667 | 8:40 | 41.67%
44 | 2020-01-30 | B22 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
44 | 2020-01-31 | B22 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
45 | 2020-01-30 | B23 | 8:00 | 1 | 8:15 | 0.6 | 8:51 | 60%
45 | 2020-01-31 | B23 | 8:00 | 1 | 8:15 | 0.4 | 8:39 | 40%
46 | 2020-01-30 | B24 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
46 | 2020-01-31 | B24 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
47 | 2020-01-30 | B25 | 8:00 | 1 | 8:15 | 0.6 | 8:51 | 60%
47 | 2020-01-31 | B25 | 8:00 | 1 | 8:15 | 0.4 | 8:39 | 40%
48 | 2020-01-30 | B26 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
48 | 2020-01-31 | B26 | 8:00 | 1 | 8:15 | 0.5 | 8:45 | 50%
49 | 2020-01-30 | B27 | 8:00 | 1 | 8:15 | 0.7 | 8:57 | 70%
49 | 2020-01-31 | B27 | 8:00 | 1 | 8:15 | 0.3 | 8:33 | 30%
50 | 2020-01-30 | B28 | 8:00 | 1 | 8:15 | 0.25 | 8:30 | 25%
50 | 2020-01-31 | B28 | 8:00 | 1 | 8:15 | 0.75 | 9:00 | 75%
51 | 2020-01-30 | B29 | 8:00 | 1 | 8:10 | 0.33333 | 8:30 | 33.33%
51 | 2020-01-31 | B29 | 8:00 | 1 | 8:10 | 0.66667 | 8:50 | 66.67%
52 | 2020-01-30 | B30 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
52 | 2020-01-31 | B30 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
53 | 2020-01-30 | B31 | 8:00 | 1 | 8:10 | 0.75 | 8:55 | 75%
53 | 2020-01-31 | B31 | 8:00 | 1 | 8:10 | 0.25 | 8:25 | 25%
54 | 2020-01-30 | B32 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
54 | 2020-01-31 | B32 | 8:00 | 1 | 8:10 | 0.5 | 8:40 | 50%
55 | 2020-02-07 | B33 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
56 | 2020-02-14 | B34 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
57 | 2020-02-21 | B35 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
58 | 2020-02-28 | B36 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
59 | 2020-02-06 | B37 | 8:00 | 1 | 8:10 | 1 | 9:10 | 100%
61 | 2020-02-06 | C1 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
62 | 2020-02-07 | C2 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
63 | 2020-02-07 | C3 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
64 | 2020-02-13 | C4 | 8:00 | 3 | 8:30 | 1.9167 | 10:25 | 63.89%
64 | 2020-02-14 | C4 | 8:00 | 3 | 8:30 | 1.4167 | 9:55 | 47.22%
65 | 2020-02-13 | C5 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
65 | 2020-02-14 | C5 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
66 | 2020-02-13 | C6 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
66 | 2020-02-14 | C6 | 8:00 | 1 | 8:30 | 1 | 9:30 | 100%
67 | 2020-02-13 | C7 | 8:00 | 3 | 8:30 | 1.8333 | 10:20 | 61.11%
67 | 2020-02-14 | C7 | 8:00 | 3 | 8:30 | 1.1667 | 9:40 | 38.89%
68 | 2020-02-13 | C8 | 8:00 | 4 | 8:30 | 2.3333 | 10:50 | 58.33%
68 | 2020-02-14 | C8 | 8:00 | 4 | 8:30 | 1.6667 | 10:10 | 41.67%
69 | 2020-02-13 | C9 | 8:00 | 3 | 8:30 | 2.5 | 11:00 | 83.33%
69 | 2020-02-14 | C9 | 8:00 | 3 | 8:30 | 0.5 | 9:00 | 16.67%
70 | 2020-02-13 | C10 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
70 | 2020-02-14 | C10 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
71 | 2020-02-13 | C11 | 8:00 | 2 | 8:30 | 1.4167 | 9:55 | 70.83%
71 | 2020-02-14 | C11 | 8:00 | 2 | 8:30 | 0.58333 | 9:05 | 29.17%
72 | 2020-02-13 | C12 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
72 | 2020-02-14 | C12 | 8:00 | 3 | 8:30 | 1.5 | 10:00 | 50%
73 | 2020-02-13 | C13 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
73 | 2020-02-14 | C13 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
74 | 2020-02-13 | C14 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
74 | 2020-02-14 | C14 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
75 | 2020-02-13 | C15 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
75 | 2020-02-14 | C15 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
76 | 2020-02-13 | C16 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
76 | 2020-02-14 | C16 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
77 | 2020-02-13 | C17 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
77 | 2020-02-14 | C17 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
78 | 2020-02-13 | C18 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
78 | 2020-02-14 | C18 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
79 | 2020-02-13 | C19 | 8:00 | 1 | 8:20 | 1 | 9:20 | 100%
79 |  | C19 |  | 1 |  | 1
80 |  | C20
84 | 2020-02-20 | D1 | 8:00 | 1 | 8:25 |  |  | 0%
85 | 2020-02-20 | D2 | 8:00 | 1 | 8:25 |  |  | 0%
86 | 2020-02-20 | D3 | 8:00 | 1 | 8:25 |  |  | 0%
87 | 2020-02-14 | D4 | 8:00 | 1 | 8:25 |  |  | 0%
88 | 2020-02-20 | D5 | 8:00 | 1 | 8:25 |  |  | 0%
89 | 2020-02-20 | D6 | 8:00 | 1 | 8:25 |  |  | 0%
90 | 2020-02-21 | D7 | 8:00 | 1 | 8:25 |  |  | 0%
91 | 2020-01-30 | D8 | 8:00 | 1 | 8:25 |  |  | 0%
93 | 2020-01-23 | E1 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
94 | 2020-01-30 | E2 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
95 | 2020-01-24 | E3 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
96 | 2020-01-30 | E4 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
97 | 2020-01-30 | E5 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
98 | 2020-01-30 | E6 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
99 | 2020-01-31 | E7 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
100 | 2020-01-30 | E8 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
101 | 2020-02-06 | E9 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
102 | 2020-02-06 | E10 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
103 | 2020-02-07 | E11 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
104 | 2020-02-07 | E12 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
105 | 2020-02-13 | E13 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
106 | 2020-02-13 | E14 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
107 | 2020-02-14 | E15 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
108 | 2020-02-14 | E16 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
109 | 2020-02-20 | E17 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
110 | 2020-02-20 | E18 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%
111 | 2020-02-21 | E19 | 8:00 | 0.1 | 8:10 | 0.1 | 8:20 | 100%
112 | 2020-02-21 | E20 | 8:00 | 1 | 8:10 | 1 | 9:20 | 100%